Progress Report
Community Plan 2022-2032
Quarter 4 2022-23 (April to March)

Summary - number of actions complete, green, amber, red and to be reported later under each Priority

Priority areas of action	Complete	Green	Status Amber	Red	To be reported later	Total
Putting learning at the centre	0	5	0	0	0	5
Our children and young people thrive	0	5	0	0	1	6
Thriving businesses and fair jobs	0	4	0	0	0	4
Caring, connected communities	0	4	2	0	0	6
People live the healthiest lives possible	0	5	0	0	0	5
Good quality, suitable housing for everyone	0	3	1	1	1	6
Total	0	26	3	1	2	32

       Key:

Statistical Measures
Project Measures

Putting learning at the centre

Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target		Latest Data
We will work with parents to support the development of babies and young children	Increase the number of children in South Lanarkshire (SIMD1/2) with no concern related to speech and language development prior to school entry	Over the last four years, the 4-5 year old review data for SIMD 1 and 2 for speech and language has been impacted by the pandemic. The recent data evidences a decrease of 2.1% in children reaching their developmental milestones on SIMD 1 with an improvement in SIMD 2. / Woodlands Nursery tested the PEEP Parenting Programme with both 2-3 and 3-5 year old children with a speech concern. They ran three separate sessions initially 5 parents in each and 6 completing. Challenges were parents working and engagement. However, for the parents that did engage they reported a benefit receiving strategies with their children and alleviating their anxiety with one dad so committed he would go to work early and come to the session before to returning to work. Some of the learning showed sessions were better indoors, in particular, with the younger age group as there were less distractions and the collaboration of the nursery and speech and language was helpful. / In January 2023, Public Health Scotland produced speech, language and communication development among children in Scotland during the COVID-19 Pandemic: whole system approach with the challenge to partners to adopt the five strands of a balanced system Family support, Environment, Workforce, Identification and Intervention. / Education and speech and language therapy	Green	2021 / SIMD 1 87.8% / SIMD 2 87%	85%		2021/22 / SIMD 1 85.7% / SIMD 2 92.5%
Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target		Latest Data
		are now focusing on developing a shared vision to generate ideas that will inform our action plan going forward to improve outcomes for children and young people with speech and language communication needs.
We will support young people to progress to further learning, work or training when they leave school	Maintain school leaver destination rate (SLDR) for all young people	The school leaver positive destination rate is 96.2%. There is no change from 2020-21. South Lanarkshire sits above the National average (95.7%) by 0.5%.	Green	2020/21 / 96.2 (SLC) / 95.5 (Scotland)	Equal to or above the Scottish Average		96.2% / (SLC) / 95.7% / (Scotland)
	Increase positive destination rate for young people progressing from the post-school AspireWorks programme	The positive destination rate for young people participating in post school AspireWorks is 81%.	Green	N/A	70%		81%

Putting learning at the centre

Action	Outcome Indicator	Comments/Progress	Status
We will work with and support people of all ages to help them re-engage with education and learning or to improve their employability skills	Learners will be offered opportunities to learn skills that meet their needs across a range of settings. We will work with learners to:- / Enhance their parenting skills / Help parents to support their child’s learning	425 learners enhanced their parenting skills through a variety of groupwork, formal and informal learning opportunities within Youth Family and Community Learning (YFCL) establishments. / 535 learners feel better able to support their child’s learning. / Programmes included structured learning such as Early Bird Plus and Incredible Years, and other programmes such as young parent groups and baby disco's etc.	Green
	We will continue to support learners to progress to other appropriate learning opportunities, ensuring that we meet ongoing needs. We will work with learners to: / Help them re-engage with education/learning / Help them access volunteering opportunities / Help them access any other appropriate learning programmes or opportunities / Improve their employability skills	822 learners have re-engaged with education or learning through work with Youth, Family and Community Learning (YFCL). / Programmes included community-based adult learning, adult literacy and numeracy programmes and English for Speakers of Other Languages (ESOL) as well as a range of opportunities for young people such as youth work with school non-attenders (e.g LEAD and Platform project). / 415 learners have accessed volunteering opportunities, both within and outwith the YFCL Service. Volunteers are referred onto a range of projects through Community Learning and Development’s Third Sector Organisations as well community groups etc. Some volunteers also work within schools or support groups to do the Duke of Edinburgh Awards etc. / 451 have accessed other learning opportunities. As above, learners will at times be signposted onto a range of learning opportunities such as Third Sector Organisations, community-based projects and school-based projects. In addition, young people will be referred onto Youth Employability programmes etc that is delivered within Education but outwith YFCL. / 862 learners over 18 years of age have improved their employability skills. Examples of this include through Adult Literacy and Numeracy Programmes, specific job support programmes for 18+ learners (to develop IT skills, CV writing skills etc.) and gardening projects that enhance the skill set of learners.	Green

Our Children and Young People Thrive

Action	Outcome Indicator	Comments/Progress			Status	Baseline		2023 Target		Latest Data
We will work to ensure children have the best start in life and become everything they can be	Percentage of schools completing a participatory budgeting process	This session 38 schools have allocated a larger % of their Pupil Equity Funding (PEF) allocation to Participatory Budgeting (PB) than in 2021-22. Only 18 schools have allocated less percentage than in 21-22, and 6 of these schools are still allocating more than the minimum 5%. Last year schools received an additional 15% uplift to their PEF allocation from the Scottish Government to support recovery post-covid. This session PEF allocations are more in-line with pre-uplift levels, and this along-with increasing staff costs have been contributory factors for the schools who have allocated less than in 2021-22. / Following revised PB training in August 2022, Participatory Budgeting Stakeholder Groups for each school led another successful PB process with the consultation now complete. / Schools are now progressing with their spend, to ensure the minimum 5% is spent in full by the end of March 2023 in line with their identified outcomes and measures. / Schools were asked to allocate a minimum of 5% of their 22-23 Pupil Equity Funding to be subject to PB this session. This collectively equates to £447,458 of SLC’s £8,949,160 22-23 PEF allocation. 66% of schools have allocated the minimum 5%, whilst 34% have allocated more than this. / The voting allocation across SLC schools comprised of: 40,106 pupils, and 10,214 parents.			Green	N/A		100%		100%

Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target	Latest Data
We will work to ensure children have the best start in life and become everything they can be	Percentage of young carers feel involved in identifying their outcomes and receive / appropriate support	Action for Children has been able to achieve over the allotted 75% in both involving young carers in identifying their outcomes and reporting yes to having received / appropriate support. The % currently sits at 100%. This is an outstanding achievement, and all credit goes to the staff and the young people involved and their families. / Here are some comments that young carers and their families have made over the last year. / A young carer who receives support said that when with the staff member they feel like they had a big sister which is what they always wanted. / “I really enjoyed today, was a bit worried I didn’t know anyone at first, but it was fun, and I’d come to something like this again if you did it”- an experience from Wiston lodge during an older group trip.		N/A	75%	100%
We will work to ensure that the health and wellbeing of children, young people and families is improved	Percentage of registered users said Kooth was effective in supporting them with their emotional wellbeing needs	860 children/young people have registered on Kooth (online counselling and emotional wellbeing platform for children and young people). Of the registered users who completed the Kooth survey, 91% found the content helpful, 95% respondents would recommend to someone else, 100% found the on-line counselling helpful.	Green	N/A	80%	100%
We will work to ensure that the life chances of children and young people in need of care and protection are improved	Percentage of young people in receipt of continuing and after care will benefit from suitable accommodation options and appropriate support	The development of a Housing Pathways Approach was continued for Throughcare Young People applying through the Throughcare System. A target of 95% was set for active throughcare homefinder applications with a person-centred housing pathway in place. 98% was achieved over 2022-23 and we continue to aim for 100% so all care experience young people have their say in seeking a suitable home.	Green	98%	95%	98%

Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target	Latest Data
We will work to ensure that the life chances of children and young people in need of care and protection are improved	Percentage of kinship carers who are surveyed at their kinship assessment will score a level of satisfaction of 4 or more with the support they received	Information is not available to report on this outcome indicator, however data will be gathered as part of planned improvement work.	To be reported later	TBC	TBC	There is no data for this specific measure / available

Our Children and Young People Thrive

Action	Outcome Indicator	Comments/Progress	Status
We will work to ensure that the health and wellbeing of children, young people and families is improved	Percentage of children and young people completing weight management interventions will report an increased awareness in the / importance of making healthy choices	Recent Scottish statistics highlight that 29.5% of children in Primary 1 were at risk of being overweight or obese (Public Health Scotland, 2021). This is an increase of 6.8% year on year. Children within the most deprived areas continue to experience higher levels of overweight and obesity with 35.7% at risk of overweight or obesity, compared to 20.8%, in the least deprived areas. / NHS Lanarkshire and associated partners continue to plan, develop and implement clinical and community-based weight management interventions to support overall Health and Well Being of children, young people and families across Lanarkshire. / By March 2023, 75% of children and young people completing weight management interventions will report an increased awareness in the importance of making healthy choices. / By March 2023, 80% of children 4-5 years old achieve a healthy weight.	Green

Thriving businesses and fair jobs

Action	Outcome Indicator			Comments/Progress			Status		Baseline		2023 Target			Latest Data
We will make it easy for businesses and social enterprises to get all available help and advice from one place	Total number of businesses/social enterprises supported / New start ups			In 2022, South Lanarkshire Council introduced a ‘small grant fund’ to provide funding to people with a robust, viable business idea who need funding to start trading. This was run by North and South Lanarkshire Councils, with investment of £350,000 from each council and was delivered in partnership with Business Gateway Lanarkshire to address a lower business start-up rate in South Lanarkshire compared to the Scottish average. Services to support new businesses include advice from a local business adviser, access to training workshops and webinars, market research and online resources to help businesses successfully commence trading. / New start-ups – 713. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.			Green		N/A		N/A			713
	Total number of businesses/social enterprises supported / Existing / organisations			The current contract with Elevator for the delivery of the Business Gateway Service in Lanarkshire has been extended for a further period to 29 February 2024. / The support provided includes dedicated (but not limited to) local business advisor to assist businesses and plan for growth, access expert help on a range of relevant			Green		TBC		TBC			1,430
Action	Outcome Indicator			Comments/Progress			Status		Baseline		2023 Target			Latest Data
				topics including Finance, HR, Digital Development and Marketing. / Existing organisations – 1,430. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.
We will make it easy for businesses and social enterprises to get all available help and advice from one place	Grants awarded to businesses/ social enterprises / Number and / value of grants			Due to demand and success of this funding, South Lanarkshire Council (SLC) have included a ‘micro grant’ offer under the new UK Shared Prosperity Fund with available grants up to £3K match. / SLC’s Business Recovery and Growth Fund (BRGF) provides larger grants targeted at existing Small and Medium sized Enterprises (SMEs) to support their strategic, longer-term sustainability and growth. This grant fund’s specific activities to help businesses adapt and grow through Capital Expenditure, Infrastructure Improvements, Training Support, Consultancy Support and Exhibition Support. / Number and value of grants - 157 - £1,340,098.61. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion			Green		TBC		TBC			157 grants issued / Value £1,340,098.61
Action		Outcome Indicator	Comments/Progress					Status	Baseline			2023 Target		Latest Data
			and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.
We will make it easy for businesses and social enterprises to get all available help and advice from one place		Grants awarded to businesses/social enterprises / Funding / leveraged	There has been significant demand for the Business Recovery and Growth Fund (BRGF) support from South Lanarkshire’s business community. In Quarter 4, BRGF has resulted in leverage of £1,495,726.53 during this period. / Funding leveraged - £3,141,967.53. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.					Green	TBC			TBC		£3,141,967.53
		Total number of jobs / Jobs safeguarded	As a result of investment via the Business Recovery and Growth Fund (BRGF), South Lanarkshire Council has seen 48 grant awards to 29 unique South Lanarkshire businesses, which will result in 299 jobs created and 957 jobs safeguarded. Businesses are also forecasting an increase in their turnover of over £13m after 12 months through BRGF support. / Jobs safeguarded – 1,273. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data					Green	TBC			TBC		1,273
Action		Outcome Indicator	Comments/Progress					Status	Baseline				2023 Target	Latest Data
			will not be available until Quarter 2, 2023-24.
We will make it easy for businesses and social enterprises to get all available help and advice from one place		Total number of jobs / Jobs created	As a result of investment via the Business Recovery and Growth Fund (BRGF), South Lanarkshire Council has seen 470 jobs created. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.					Green	TBC				TBC	470
		Total number of jobs / Increase in / Turnover	As a result of investment via the Business Recovery and Growth Fund (BRGF), South Lanarkshire Council has seen an increase in turnover of £21,836,790. / This Lanarkshire wide activity is part funded by EU Funds (European Regional Development Fund), led by North Lanarkshire Council and runs from January to December. The programme completion and data gathering is not complete for 2022-23, therefore the baseline; target and latest data will not be available until Quarter 2, 2023-24.					Green	TBC				TBC	£21,836,790

Thriving businesses and fair jobs

r Children and Young People Thrive
Action	Outcome Indicator	Comments/Progress	Status
We will work to ensure everyone has the same opportunities to learn new skills	Deliver responsive employment support and measure the number of successful employment outcomes	As at March 2023, there have been 1,687 engagements within Employability Services, of which 238 entered employment. / Recruitment fairs were also held during 2022-2023, which resulted in 29 job outcomes with recruitment still ongoing. / The Making It Work and GATEWAY Employment programs resulted in 273 job outcomes.	Green
	Promote opportunities and careers and measure successful training outcomes	During the year 2022-23, Employability Services helped 536 clients undertake vocational training, including the Making It Work and GATEWAY Employment programs. Upon completion, a number of clients secured a range of outcomes including jobs, promotion and salary increase.	Green
We will ensure that the place where you live is at the heart of our response to the climate emergency and help places to become sustainable	Monitor and deliver town centre measures and initiatives in line with town strategies, Community Wealth Building and 20 Minute Neighbourhood approaches. / Town Centre Vacancy Rates – maintain at or below national averages / Businesses supported (including Social Enterprise) – support across towns and places	South Lanarkshire Council are working with the key stakeholders across all our town centres to support businesses and invest in projects and initiatives which support the evolving way in which our towns are used by local communities. / In relation to vacancy rates, all our towns, with the exception of East Kilbride, are maintaining levels at or slightly below the national average of around 14%. The council are seeing a move to more service-based businesses and more local traders which is an encouraging trend and where possible are supported through business support. The number of businesses supported will be available at a later date. / East Kilbride has vacancy levels (c30%) well beyond the national levels and our own targets of circa 12% but is subject to a masterplan process to seek to address these challenges and bring it back to a more sustainable position.	Green

Caring, connected communities

Action	Outcome Indicator	Comments/Progress			Status	Baseline		2023 Target	Latest Data
We will continue to support and encourage every community to identify and act on their local priorities	Increase engagement of those within neighbourhood planning areas in place based participatory budgeting programme	Place based participatory budgeting has been completed in Hillhouse, Udston and Burnbank (HUB), Burnhill, Springhall and Whitlawburn and Cambuslang East. / Participation rates have increased since 2021-22 and the review of the local plans has begun in Fernhill, Whitehill, Fairhill and Blantyre.			Green	3,571 participants / 2021-22		10% Increase	3,751 / participants
	Increase the number of local community plans through promotion of opportunities for communities to create their own plans and identify priorities	Local plans have been completed for all 9 of the urban neighbourhood planning areas and published in 2022-23. Many of the areas are now refreshing their plans and this will continue throughout 2023. / The council’s Community Engagement Team has also worked with a range of communities in Clydesdale and East Kilbride to look at local community led plans in Lanark, Carluke, Greenhills, Biggar, Lesmahagow, Duneaton, Carstairs Junction, Carnwath, Coalburn and Forth. New plans are being developed in Dolphinton, Crawford, and Meikle Earnock, Hamilton.			Green	17		20% Increase	21

Caring, connected communities

Children and Young People Thrive
Action	Outcome Indicator	Comments/Progress	Status
We will bring communities together to share priorities and work jointly on them	Development of a further two community partnerships in Hamilton and East Kilbride areas	A second meeting of the East Kilbride Community Partnership was held mid-January 2023 with further development work required to increase the current membership. During February/March, officers from the council’s Community Engagement Team attended meetings of local groups to encourage participation. / Development work has restarted to establish a Community Partnership for Hamilton and the surrounding areas, and meetings are taking place with local groups to discuss the benefits of joining the partnership.	Green
	Hold a networking event for representatives of community led plans to come together and discuss progress and next steps across South Lanarkshire	Due to changes within the Community Engagement Team, SLC this networking event will now take place in Winter 2023.	Amber
	Representation of all 4 community partnerships at Board level	Representatives of the Cambuslang/Rutherglen and Clydesdale Community Partnerships are now members of the CPP Board and provide quarterly reports to the Board. / Officers within the council’s Community Engagement Team, are progressing work to establish and maintain the Hamilton and East Kilbride Community Partnerships to enable representation of these groups to the CPP Board.	Amber
We will involve local representatives in community planning at all levels, including on the Community Planning Partnership Board	Neighbourhood planning stakeholder groups to be supported to develop local leaders through capacity building and training support	Two Activate Community Learning Courses around community involvement were developed in 2022-23 run by Glasgow University with accreditation for participants and a route into further education. / 18 participants finished the first course and there are 12 scheduled to finish the second course. Representatives from Cambuslang and Rutherglen and Clydesdale Community Partnerships have attended and participated in two CPP Board meetings.	Green

People live the healthiest lives possible

 Children and Young People Thrive
Action	Outcome Indicator	Comments/Progress	Status
We will ensure that all of our services work with people as early as possible to stop problems happening	Implement Discharge Without Delay to return people to their home or community safely	Discharge Without Delay has been implemented Lanarkshire wide. There is a particular focus on implementing Planned Date of Discharge (PDD) which means early referral to Social Work to allow for people to have an early plan in relation to discharge, this in turn ensures a more focused application of care and care placements. / PDD should be set within 48hrs of admission to acute or community hospitals. Setting the PDD is a multi-agency responsibility (health, social work and others). This also means people are less likely to be delayed in their discharge. Currently patients are discharged 91% on or before their PDD. In addition, the Home First model is being rolled out to all localities on a locality-by-locality basis. Capacity of Integrated Care and Support Teams have been boosted.	Green
We will increase access, activities and supports that help improve mental health and addictions	Further develop mental health services to support more people to recover or manage their condition successfully and live as happy, healthy and productive lives as possible.	The Primary Care Mental Health & Wellbeing Service is accessible to 88 GP Practices across Lanarkshire. In 2022, Assessment Plus was established within the Mental Health and Wellbeing Service and as of May 2023 is now available in three localities (East Kilbride, Clydesdale and Hamilton). / Assessment Plus aims to increase accessibility to evidence-based psychological therapies within Primary Care. The service is designed to meet the needs of adults who have mild to moderate, psychological problems and could benefit from specialist psychological assessment and brief, low-intensity intervention. The Third Sector service was commissioned to deliver non-clinical interventions within localities. The test of change ongoing for ability for Care Navigators within GP surgeries to directly refer to primary care mental health staff.	Green

Action	Outcome Indicator	Comments/Progress	Status
We will increase access, activities and supports that help improve mental health and addictions	Work with South Lanarkshire Alcohol and Drug Partnership to reduce the impact of addictions within our communities through early intervention/prevention and a focus on recovery	The South Lanarkshire Alcohol and Drug Partnership (SL ADP) continues to work with strategic objective and five priority areas, two of which are early intervention and prevention and a recovery oriented system of care (ROSC). / Turning Point Scotland was commissioned through the ADP to deliver an adult outreach service in January 2022 for a period of three years. This service works in alignment with statutory treatment services, offering a case management approach and close one-to-one. / The first responder and recovery ‘Beacons’, commissioned through the Third Sector Organisation ‘Liber8’, has just opened its fourth Beacon in East Kilbride. The ‘Beacons’, established as a prototype model, continues to augment statutory services and now provides all four localities in South Lanarkshire with a first responder and recovery beacon which operates through employing a whole family approach. At a recent national conference, South Lanarkshire was singled out for its innovative approaches in both the Beacons model and in promoting a family centered service delivery.	Green

Action	Outcome Indicator	Comments/Progress	Status
We will provide high quality day-to-day health and social care services that are accessible to everyone in our community who needs them	Deliver all services in line with statutory requirements to ensure people are safe and healthy and encouraged to meet their personal outcomes	The priority is to ensure effective delivery of critical services, complying with statutory legislation to protect vulnerable children, young people and adults in our communities. Services remain committed to assessing those most at risk with the focus on public protection. / The outcome of a Joint Inspection of Adult Support and Protection carried out in August/September 2022 confirmed that our local partnership had strengths in key processes and strategic leadership.	Green
	Support carers to maintain their caring role through a personal outcome approach	Partnership working is thriving and enhancing support to carers through the dedicated work of our commissioned provider Lanarkshire Carers. Adult Carer Support Plans (ACSP) specifically focus on the personal outcomes of Health and wellbeing; finances; living environment; relationships; life balance; employment and training; and future planning. / In 2022-23, Lanarkshire Carers progressed 912 ACSPs and made 883 wellbeing calls to carers. They allocated over £51,000 in direct grants to carers in support of identified personal outcomes. They have recently been awarded Carer Positive Status (Employer in Scotland) at the Exemplar level.	Green

Good quality, suitable housing for everyone

Action	Outcome Indicator	Comments/Progress			Status	Baseline		2023 Target	Latest Data
We will increase affordable housing supply and improve access to and choice of housing options that suit people’s needs	Increase the number of additional new affordable homes added to the housing supply in South Lanarkshire	In 2022-23, the council’s Affordable Housing Supply Programme continued to deliver homes across South Lanarkshire, including 233 new council properties and 57 purchased by the council.			Green	0		By 250-300 per year	233
	Increase the number of people accessing Housing Options Services	There has been a significant focus on the development of homelessness prevention services in recent years and in particular on developing the Housing Options Service as the first response to emerging housing need and risks. / The slight reduction in the number of housing option interviews in the year can be attributed to emerging changes within the private rented sector and the cost-of-living crisis which have adversely impacted on prevention opportunities.			Amber	964		Over 1,000 per year	972

Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target	Latest Data
We will work in partnership to improve housing quality and energy efficiency, whilst supporting a just transition to decarbonisation	Increase the average Standard Assessment Procedure (SAP) score of all homes with an Energy Performance Certificate in South Lanarkshire	South Lanarkshire Council continues to promote and support energy efficiency improvements to homes across South Lanarkshire. / For those who own their home, the council facilitates and administers national grant funding to enable owners to make improvements, including the Energy Efficient Scotland: Area Based Schemes and the Energy Company Obligation (ECO). The fourth phase of ECO will be launched in South Lanarkshire later in 2023, with the previous phase / resulting in over 2,600 homes being improved. / For the private rented sector, landlords are encouraged and supported to access national funding to make improvements through the twice annual Landlord Forum hosted by the council and where information is circulated from partner services. / For the council’s own homes, significant investment continues to take place to improve energy efficiency and work towards national net-zero targets. This sustained investment has led to an average SAP score of 71 for council properties, contributing to a reduction in the energy required to be used by tenants. / For all tenures, the average SAP score is 66.	Green	65.1	Increase from baseline	66
Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target	Latest Data
We will work in partnership to improve housing quality and energy efficiency, whilst supporting a just transition to decarbonisation	Increase the percentage of socially rented properties achieving the Energy Efficiency Standard for Social Housing 2 (EESSH2)	In September 2022, the Scottish Government suspended the use of EESSH2 as a measure of progress. / Currently awaiting the outcome of the national review which will establish new national energy efficiency/ decarbonisation measures.	To be reported later	Not available	Not available	Not available
We will work in partnership to prevent and significantly reduce homelessness, and improve outcomes for those at risk of or who experience homelessness	Reduce the level of Homeless Households (homelessness caseload at year end)	In the previous year the Rapid Rehousing Transition Plan (RRTP) review noted significant success against a wide range of homelessness outcome measures. Within the current year however, there has been a considerable increase in demand for homelessness services locally and nationally. / The RRTP target of reducing / homelessness caseload by 10% - 20% has not been achieved in the year due to the significant increase which took place in demand for homelessness services. / The forthcoming RRTP review will consider the need for a revised target to be set. / Services continue to support households with the overall aim of avoiding homelessness where it is possible to do so.	Red	892	Reduce from baseline by 10%-20%	1,331

Action	Outcome Indicator	Comments/Progress	Status	Baseline	2023 Target	Latest Data
We will work in partnership to prevent and significantly reduce homelessness, and improve outcomes for those at risk of or who experience homelessness	Increase the percentage of former homeless households provided with a social rented tenancy that maintain their home for more than 12 months	A range of internal and Third Sector partners continue to deliver housing support services, both in prevention activity and response to homelessness to minimise its impact. / Monitoring of housing support outcomes reflect positive outcomes, reduced need across all wellbeing/ support need indicators and increasing tenancy sustainment.	Green	88%	Increase from baseline	90.5%