Report	Agenda Item

Report to:	Performance and Review Scrutiny Forum
Date of Meeting:	19 August 2025
Report by:	Executive Director (Finance and Corporate Resources)

# Council Plan Connect 2022-2027: Quarter 4 Progress Report 2024-2025

## Purpose of Report
1.1	The purpose of the report is to:
provide the Council Plan Connect Quarter 4 Progress Report 2024-2025, for the period 1 April 2024 to 31 March 2025
## Recommendations
2.1.	The Forum is asked to approve the following recommendations:
(1)	that the Connect Quarter 4 Progress Report 2024-2025 summarised at paragraph 4.5. and can be viewed CMIS>Meeting Calendar Agenda Item 3 Q4 Appendix 1;
(2)	that the key achievements, as detailed in paragraph 4.6. of this report be noted.
(3)	that the additional scrutiny of measures that have changed status between Quarter 2 and Quarter 4 as summarised at paragraph 4.7. and detailed at Appendix 1 of this report, be noted; and
(4)	that the Strategic subset of LGBF Results, as detailed at paragraph 5. and CMIS>Meeting Calendar Agenda Item 3 Q4 Appendix 3, be noted
## Background
3.1.	The Council Plan Connect covering the period 2022-27 was approved by the full council at its meeting on 15 June 2022. The plan sets out the council’s vision, values, priorities and outcomes for the five-year period.

3.2.	As part of the performance reporting arrangements introduced in 2007, it was agreed that progress reports on the Council Plan would be provided at the mid-year point (Quarter 2) and at the end of the financial year (Quarter 4). This report provides a summary of progress on Connect as at the end of Quarter 4, 31 March 2025.
## Quarter 4 Progress 2024-2025
4.1.	The Council Plan offers flexibility, both at the Resource level and from one year to the next, in the choice of actions and measures required to deliver the council’s outcomes. Alongside this flexibility, however, comes the requirement to ensure that the golden thread from Council Plan to Resource Plan remains unbroken.

4.2.	The reporting framework for the Council Plan identifies key measures within Resource Plans which are taken and combined in a Connect report to provide a balanced picture of council performance against Connect outcomes.

4.3.	A total of 256 measures have been identified from the 2024-2025 Resource Plans. Of those, 61 (24%) have been nominated as key strategic measures for reporting progress against Connect.

  1. Progress to date against all measures is contained in the Connect Quarter 4 Performance Report 2024-2025, attached as Appendix 1. This report has been produced from the council’s performance management reporting system IMPROVe, and uses a traffic light format with the following definitions to give a status report on each measure:

Status	Definition
Blue	Project complete
Green	The timescale or target has been met as per expectations
Amber	There has been minor slippage against timescale or minor shortfall against target
Red	There has been major slippage against timescale or major shortfall against target
Report later	The information is not yet available to allow us to say whether the target has been reached or not. This will be reported when available
Contextual	Included for ‘information only’, to set performance information in context

4.5.	To ensure adequate scrutiny of performance across all Resources, individual Resource committees receive details of all ‘red’ measures relating to that Resource including management actions, where applicable. In addition, the council’s Performance and Review Scrutiny Forum may consider those measures across all Resource Plans reporting a ‘red’ and/or ‘amber’ status.

The overall summary of Connect progress to date is as follows:
Status	Statistical Measures	Project Measures	Total Measures	%
Blue	N/A	6	6	10%
Green	26	17	43	70%
Amber	4	2	6	10%
Red	4	0	4	6%
Report later/Contextual	1	1	2	4%
Totals	35	26	61	100%

Data as at 12 June 2025 v2

4.6.	Progress for 2024-2025 against each of the six Connect Outcomes and the related achievements have been summarised in the following tables:

4.6.1.
Connect Outcome - Communities and Environment

Number of measures

Blue / 1	Green / 11	Amber / 3	Red / 2	Report later / 0	Total / 17

Achievements
- In 2024-2025, South Lanarkshire University Health and Social Care Partnership received a total of 685 stories from service users, patients, their families and carers via Care Opinion. Care Opinion is enhancing our understanding of people’s experiences with health and care and has been crucial in helping us build on our strengths while also identifying areas for improvement, allowing us to make targeted refinements wherever appropriate.
- The Community Wish List has continued to thrive, with 36 Community Wishes received from a range of community groups across South Lanarkshire. 23 Wishes have been answered, with a range of financial donations, goods and materials, reallocation of furniture items from South Lanarkshire Leisure and Culture (SLLC) property (totalling £27,918). To date this financial year, the project has totalled over £83,000
- The percentage of household waste sent to landfill in the period January to December 2024 was 1.32%, well within the target of below 5%.
- The percentage of properties with Full Fibre Connection has increased to 58.8% in 2024-2025, exceeding the annual target to reach 43% coverage.
- A programme of bridge and other structure projects has been implemented, including the £9.4million replacement of the Clyde Bridge.

4.6.2.

Connect Outcome - Education and Learning

Number of measures

Blue / 1	Green / 2	Amber / 1	Red / 0	Report later / 0	Total / 4

Achievements
- SQA examination results for the 2024 exam diet were published by SQA on 6 August 2024. SLC pupils were presented for over 80,000 qualifications at National 5, Higher and Advanced Higher levels. When compared with National pass rates (based on entries in other Local Authorities) attainment levels in SLC are above the National Pattern.
- An increasing percentage of our primary schools are now offering play-based learning at each stage between Primary 1-3. There is also one establishment implementing this approach across a P1-4 class.
Primary 1: Approximately 79.4%
Primary 2: Approximately 53.7%
Primary 3: Approximately 24.1%
- 29 of our schools have now achieved the highest gold level in the Scottish Book Trust Reading Schools framework. A further 22 have silver status and 35 have accredited status. This respected framework is linked to How Good is Our School 4 (HGIOS4) and aims to build an inclusive reading culture in schools. Our levels of award are comparatively very high and are reflected in the continuing improvement in our literacy attainment levels.
- Another successful Conference of Schools (CoS3) event took place this year. Designed and delivered by our young people for our young people, the event provided a valuable platform to educate, inspire and engage on these matters. The event was again well attended and received significant praise from Education Scotland’s Chief Executive who visited on the day.
- The Instrumental Music Service (IMS) featured 12 diverse performances from mainstream and ASN schools in the 12 Days of Christmas event. Throughout December the IMS supported over 100 school concerts, community events and services.

4.6.3.
Connect Outcome - Health and Wellbeing

Number of measures

Blue / 0	Green / 6	Amber / 2	Red / 0	Report later / 1	Total / 9

Achievements
- Of the 50 new homes completed to date in 2024-2025, all have been built to ‘Housing for Varying Needs’ standards and are easily adaptable to accommodate tenant’s changing needs over time.
- 8 of the 50 (16%) were accessible for wheelchairs, exceeding the target of 10% established in the Local Housing Strategy 2022-27. The homes are located close to existing services, amenities and transport links allowing tenants to easily connect with the existing community within Brackenhill Farm.
- The council’s affordable housing supply programme continues to increase the supply of council homes across South Lanarkshire, with a focus on ensuring that the new homes provide for changing in peoples need over the course of time.
- Equal Say, the adult Advocacy commissioned service, completed its first year of operation in October 2024. Quarterly reports show increased activity in referrals of over 150 per quarter, and prominent advocacy issues associated with Mental Health Legislation, Adults with Incapacity, and Adult Support and Protection.
- Lanarkshire Advocacy Planning Working Group is refreshing the Lanarkshire Advocacy Plan 2020-25 ensuring that Advocacy supports the voice of service users and carers and the importance of those Advocacy services to the most vulnerable groups within our communities.
- Lanarkshire Carers continues to develop and evolve its “CarerSpace” online portal to start or continue a conversation. It is a toolkit developed by carers for carers that helps explore various aspects of a carer’s life, focusing on what matters to them. Once submitted staff from Lanarkshire Carers can pick up the conversation with the carer.
- Take Control, the commissioned service for independent advice and information on Self Directed Support, has worked with 400 South Lanarkshire residents to exercise choice and control over their care and support arrangements.
- See Hear Strategic Working Group hosted an information event in Hamilton on 29 May 2024. Twenty-two organisations contributed to the event focused on sensory services for hearing and sight. The Director attended the event, thanking all the services for their continued support to South Lanarkshire Residence.
- Care at Home teams, including Home Assessment, have been subject to inspection by the Care Inspectorate during 2024-2025. The feedback has been positive throughout with almost all areas of inspection graded as ‘very good’ or ‘good’ and inspectors highlighting significant strengths in relation to the delivery of care; positive outcomes for people; strong leadership; and a highly trained workforce. The gradings and positive feedback are testament to the substantial programme of redesign and modernisation over the last five years in response to the serious concerns identified by the Care Inspectorate in 2019.
- Work on Cost of the School Day was presented at the national Facing Up to Poverty in Schools Network and highlighted as an example of good practice.
- The £13m Transition Fund is helping to modernise the leisure and culture assets. Phase 1 (£8.5m) spend underway. Phase 2 projects were approved at Executive Committee on 13 November 2024 and are now being progressed.
- Works on the six play areas identified for investment, as part of the multi-year Play Area Investment Programme, are now complete.
- Consultation on play areas has been undertaken with local members and communities in the Hamilton area.

4.6.4.
Connect Outcome - Children and Young People

Number of measures

Blue / 1	Green / 2	Amber / 0	Red / 0	Report later / 0	Total / 3

Achievements
- 100% of young people leaving care were provided with a housing options discussion which resulted in the development of an individual housing plan. 100% were supported to move onto suitable accommodation.
- A new partnership project, led by Social Work and Housing in cooperation with Barnardo’s and supported by the National Lottery Community Fund, has been helping young people transition from care into their own accommodation. The project was developed with the assistance of the members of the South Lanarkshire Champions Board, a group of care-experienced young people who advocate for the needs of their peers and shape services within the South Lanarkshire area.
The Futures project provides wrap around support to young people leaving care and moving to independent living for the first time. This is done by providing four, furnished training flats together with intensive support to assist the young people in developing skills for setting up their home, maintaining a successful independent tenancy and building local community connections and networks before moving to fully independent living.

4.6.5.
Connect Outcome - Housing and Land

Number of measures

Blue / 2	Green / 9	Amber / 0	Red / 1	Report later / 0	Total / 12

Achievements
- We continue to increase the supply of affordable housing with the delivery of 180 homes delivered during 2024-2025. This includes 50 new build and 130 properties acquired through the market purchase scheme.
- 91.9% of tenancies were sustained for more than a year.
- Average days to relet a property decreased from 22.15 days in 2023-24 to 19.31 days in 2024-2025.
- 99% of reactive repairs were completed right first time.

4.6.6.
Connect Outcome - Our Economy

Number of measures

Blue / 1	Green / 10	Amber / 0	Red / 1	Report later / 1	Total / 13

Achievements
Support for businesses in South Lanarkshire has exceeded the set targets against the following measures:
- the number of business support interventions per annum by Economic Development was 1,014 (target 800)
- the number of jobs created or sustained as a direct result of Economic Development intervention was 1,071 (target 500)
- increased value of sales generated by businesses as a direct result of Economic Development intervention was £8.532m (target £5m)
A range of business programmes, services and events have been delivered, including:
- Food and Drink: the council financially and practically supported the Lanarkshire Larder.
- Tourism: the council has delivered a range of projects to support tourism in the area, such as a travel trade programme to help businesses that operate primarily in the tourism sector to become ready to work with the travel trade.
- Construction: Build Lanarkshire Programme was successfully delivered by the council in conjunction with North Lanarkshire and Hub South West.
- Young Enterprise: the council successfully delivered the inaugural Shark Reef initiative aimed at promoting entrepreneurship to S3 pupils.
- Meet the Real Buyer event: Co-delivered, successfully enabling local businesses to speak to public and private sector buyers.
- 3,059 participants have been supported on council-operated employability programmes; over double the 1,500 target.

4.6.7.	In addition to working towards the six Connect Outcomes, the council will continually aim to improve and ensure effective and efficient use of resources, and that business will be conducted with integrity and transparency and will operate to the highest standards. In order to monitor and report progress against these values, Resource Outcomes have also been identified, under the heading Delivering the Plan and achieving Best Value. Related achievements to date are summarised in the following table:

Delivering the Plan and achieving Best Value

Number of measures

Blue / 0	Green / 3	Amber / 0	Red / 0	Report later / 0	Total / 3

Achievements
Against an extremely challenging set of socio-economic circumstances, positive performance, against previous year, was achieved in relation to:
- the percentage of rent collected which increased from 99.5% Quarter 4 (2023-24) to 100.2% in Quarter 4 (2024-2025).
- the percentage of gross rent arrears reduced over the same period from 8% Quarter 4 (2023-24) to 7.1% in Quarter 4 (2024-2025)
- As part of the Glasgow City Region Smart and Connected Social Places (SCSP) 5G Innovation Fund, South Lanarkshire University Health and Social Care Partnership has engaged with Care Messenger Holdings Ltd to deliver an innovative project that provides commercial LG Smart TV products to residents living within David Walker Gardens care home for older people. Residents who wish to participate in the project can communicate directly via text message or video call with care home staff, their families, befrienders or other professionals, via their TV. Initially 20 TVs were installed within residents' rooms, and this has since been offered to all 50 residents across the whole care home. Early evaluation indicates a positive impact on social isolation and loneliness.
- The audited Accounts for 2023-24 were produced and received a clean audit certificate. These were approved for signature by the Risk and Audit Scrutiny Committee before the submission date of 30 September 2024.
- With assistance from the Improvement Service, the council developed an SLC-focused Local Government Benchmarking Framework (LGBF) dashboard reflecting the council's strategic priorities as set out in the Council Plan, Connect. Following presentation at the PRSF on 28 May 2024, the dashboard was made available to the public via a link on the performance pages of the council's website.
- Year two of the three-year Frontline First Fund (totalling £3.5million) is fully implemented. Major improvements include refurbishment of Carluke marketplace, Blantyre miner’s monument, ongoing repair of Lanark Loch walkways, shrub bed removal Westwoodhill, East Kilbride.

4.7.	Scrutiny of change in measure status
A further analysis introduced to aid scrutiny of performance, is to highlight and explain all measures that have changed status from Quarter 2 to Quarter 4. On analysis of these, five measures improved, and five measures showed a decline in performance - details of which are included at Appendix. The remaining measures under scrutiny showed a change from Green or Report later to Blue complete)/Green and need no further action.

## Strategic subset of Local Government Benchmarking Framework (LGBF) Results
5.1.	As agreed at the Performance and Review Scrutiny Forum on 21 March 2023, this report includes a new Appendix 3 which focuses on a subset of LGBF indicators aligned to the outcomes in the Council Plan. This provides an opportunity to review benchmarking indicators which are of strategic importance to the council and gives insight into the council’s performance over time as well as comparison with national average.

5.2.	As well as featuring in this report, LGBF indicators continue to be reported annually in full to the Performance and Review Scrutiny Forum and included in the council’s public performance reporting arrangements, published on the council’s website.

## Employee Implications
6.1.	The outcomes noted within the Council Plan inform the Resource Plans and in turn the Performance Appraisal process for individual employees.

## Financial Implications
7.1	Provision for meeting the Council Plan’s outcomes is reflected in both the Revenue and Capital budgets, and longer term, within the framework of the council’s approved Financial Strategy.

## Climate Change, Sustainability and Environmental Implications
8.1.	There are no climate change, sustainability or environmental implications arising from this report.

8.2.	The council acknowledges the serious and immediate threat of climate change and is committed to accelerating the pace of action in response to the climate emergency and in Scotland’s transition to a net-zero and climate resilient society and economy. All Resource Plans have recognised sustainable development and climate change as a key area of focus for 2024-25.

## Other Implications
9.1.	A significant element of the delivery of the outcomes in the Community Plan 2022 to 2032 will come through the achievement of the actions contained within Connect.

## Integrated Impact Assessment and Consultation Arrangements
10.1.	This report does not introduce a new policy, function or strategy or recommend a change to an existing policy, function or strategy and therefore no impact assessment is required.

10.2.	There is also no requirement to undertake any consultation in terms of the information contained in this report.

Paul Manning
Chief Executive

14 July 2025

Link(s) to Council Values/Priorities/Outcomes
The Council Plan 2022-27 reflects the overarching vision of South Lanarkshire Council and details its values, priorities and outcomes, including links to the Community Planning Partnership

Previous References
Connect Quarter 4 Progress Report 2023-24

List of Background Papers
Council Plan Connect 2022-27: approved by South Lanarkshire Council on 15 June 2022

Contact for Further Information
If you would like to inspect the background papers or want further information, please contact:
Tom Little, Head of Communications and Strategy
Ext : 4904 (Phone: 01698 454904)
Email : tom.little@southlanarkshire.gov.uk
Performance : www.southlanarkshire.gov.uk/performance

If you need this information in another language or format, please contact us to discuss how we can best meet your needs. Phone 0303 123 1015 or email equalities@southlanarkshire.gov.uk

## Appendix 1 Connect: Quarter 2 to Quarter 4 2024-25 - scrutiny of change in measure status

Performance has improved from Q2 to Q4
Measure	Q2 Status	Q4 Status	Q4 Comments
Percentage of reports submitted to the Children’s Reporter within agreed timescales (SWR)	Red	Amber	To date, the percentage of reports submitted to the Children's Reporter within timescale is at 72%. Increased monitoring and regular meetings with the Scottish Children's Reporters Administration has improved performance from 85% in Quarter 3 to 91% in Quarter 4.
Number of business support interventions per annum by Economic Development (grants, loans or advice) (CER)	Amber	Green	The majority of business support interventions were made up of registration and event attendance via the Supplier Development Programme (SDP). The number of interventions in 2024-2025 was 1,014, exceeding the target of 80
Embed the principles and practices in the Inclusion Framework across schools, to improve outcomes for children and young people, and provide a progress report to the Education Resources Committee (EDR)	Amber	Blue	The Framework has been distributed in hard copy to all education establishments. It is also available on the council intranet and on Glow. Feedback is very positive from schools regarding the regular use of this resource and has built capacity in staff to manage tasks related to inclusive education.
Continue to implement the Rapid Rehousing Transition Plan (RHTP) (HTR)	Red	Blue	RHTP is fully complete. Homeless Strategic Plan approved at HTR Committee on 16 September 2024.
Delivery of the Levelling Up Fund grant funded projects through the Clydesdale Way and Shawfield Remediation with a value of £6.7m in 2024-2025 (CER)	Amber	Green	Clydesdale Way: The Grant Award Agreement with Dumfries and Galloway Council (the lead authority for this joint project) has been finalised. Turner and Townsend have been appointed to project manage the design and delivery of the project. / Shawfield: Clyde Gateway have commenced delivery of the project, with the original programme on schedule as at 31 March 2025.

Performance has declined from Q2 to Q4
Measure	Q2 Status	Q4 Status	Q4 Comments
Percentage of our road network that should be considered for maintenance treatment (CER)	Report Later	Red	This figure is derived from the Society of Chief Officers of Transportation in Scotland (SCOTS) Road Condition Index (RCI) survey which is undertaken each year. The target figure of 31.9% is based on the results for the period 2022-24. The actual figure for 2023-25 at 32.5% indicates a regression of 0.6% of the amount of our road network in an amber or red status. Deterioration is also showing across individual road categories to a similar extent.
Percentage of total household waste that is recycled in 2024 (CER)	Amber	Red	This measure is reported per calendar year. The year-to-date figure reflects performance from January to December 2024, which remains below the target of 50%. / To help move closer to the target, Waste Services are doing the following: / Extending recycling services at flatted properties to include those that have typically had low participation rates / The Waste Education Team continue to work with residents across South Lanarkshire to improve recycling knowledge and participation / Actively monitoring changes in national legislation and guidance / Performance will continue to be closely monitored.
Percentage of children and young people attending secondary school	Report Later	Amber	Although the figure to date falls below the target set there is an improvement on the 2023/24 figure of 87.7%
Percentage of pupils entering positive destinations (initial destinations) (EDR)	Green	Amber	3,625 young people left school in 2023-24 and the positive destination rate decreased by 0.5 percentage points to 96.4% compared with the previous year. South Lanarkshire has maintained a positive rate higher than the National average of 95.7%. Discussions are taking place with all schools and Skills Development Scotland to discuss those young people in negative destinations and identify any lessons learned.
Number of new South Lanarkshire business starts supported by Business Gateway (CER)	Amber	Red	This year represents a transition for the Business Gateway, changing from a contract based external provider model, to an in-house model which will reflect a more customer focused, rather than target driven, delivery model. The transition led to a significant disruption to the service. Through the revised customer focused service approach appropriate target levels will be established going forward