## Contents

## Foreword
Councillor Davie McLachlan
Chair of Housing and Technical Resources Committee
I am pleased to report that that the fourth year of South Lanarkshire’s Rapid Rehousing Transition Plan has been another successful one despite the significant challenges we have faced over the last 12 months. The marked increase in demand for homelessness services which has been experienced locally and nationally during the year has bucked trends reported in previous years RRPT reviews. Once again however local services have stepped up to meet the challenges, preventing homelessness where possible, otherwise providing appropriate accommodation and support services to meet individual needs whilst also meeting unprecedented and wide-ranging needs arising from humanitarian programmes, in particular from Ukraine.
This review shows the breadth of work that has been undertaken over the year and the ongoing commitment to delivering quality, person centred services to achieve positive and sustainable outcomes. We have now moved beyond our commitment to deliver 1,000 additional council homes by setting a new target of an additional 1300 homes by 2027. Working collaboratively with our housing association partners to deliver a significant increase in additional affordable homes which is key to achieving the significant reduction in homelessness at the heart of our plan.
As we move forward into year five, the final year of the plan, I am confident that we will continue to build on the good work and outcomes already achieved despite the challenging context. Ensuring we maximise opportunities to increase the supply of affordable housing, prevent homelessness wherever possible or effectively respond with appropriate packages of accommodation and support as our foundation for delivering the impact on homelessness and individual outcomes which we seek to achieve over the remaining year of the plan.

Councillor Joe Fagan
Chair of South Lanarkshire’s Community Planning Partnership Board
Over the past year, our communities have faced real challenges in terms of meeting their basic needs and this year’s review demonstrates the scale and nature of the efforts that partners have directed towards tackling homelessness in what has been the most difficult of circumstances.
This review highlights just some of the excellent work that is being delivered across the Community Planning Partnership every day to improve the lives of people in South Lanarkshire. Over the last year the focus has remained on prevention of homelessness and where prevention is not possible to minimise the impact on individuals, families and communities through rapid provision of quality temporary housing, based on our model of temporary housing being ordinary homes within ordinary communities, quality trauma informed housing and homelessness services including specialist support services where required to meet the needs of some of the most vulnerable people in our society.
We must continue to work together, utilising the strength of the Community Planning Partnership to understand need, respond effectively to increased pressures and continue our path to achieving change in addressing homelessness across South Lanarkshire over the final year of the Plan and beyond.

## Executive Summary
Effective partnership working and a shared commitment to addressing homelessness has enabled good progress to be made over the period since South Lanarkshire’s Rapid Re-Housing Transition Plan (RRTP) was approved. Indeed, the position recorded at the end of the previous year noted the scale of the progress which had been made in preventing and resolving homelessness, including;
- a 21% reduction in overall homelessness,
- a 25% reduction in long term homelessness (households residing in temporary accommodation for over 12 months),
- a 22% reduction in time spent in temporary accommodation by households with children and
- a reduction of 8% in the number of children affected by homelessness.
2022/23 has however proven an extremely challenging year both locally and nationally in terms of maintaining progress, with a 17% increase in homeless presentations in South Lanarkshire accompanied with a 38% increase in homelessness since 2021/22. Nationally it has been reported that homelessness figures are at the highest they have been since records began in 2002.
In reviewing the fourth year of the plan the Homelessness Strategy Group reflected on the changing environment in which partners operate, not least the national spike in homelessness, the cost-of-living crisis and wider increasing demand and pressures in the housing system, including from humanitarian programmes.
Notwithstanding this context the partnership has reiterated its ongoing commitment to working over the longer term to prevent homelessness wherever possible and support those at risk of or who are experiencing homelessness. A summary of the key highlights over the last year, the fourth year of the RRTP include: -
- A continued reduction in long-term homelessness, with 67% fewer homeless households living in temporary accommodation for more than 12 months over the lifespan of the plan.
- A further 3.7% reduction in the number of days people resided in temporary accommodation now 174 days.
- The avoidance of homelessness in 65% of cases through positive prevention activity by the Councils Integrated Home Options service.
- Continued success in the pathway plan approach to meeting the housing needs of care experienced young people, with 100% (51) over the last year having a completed pathway plan. Of the 51 young care leavers seeking housing 30 have had tenancies secured and 7 are under offer, increasing average age for move onto independent living to 21. The sustainability for this group is positive with 93% of tenancies sustained over last year.
- Continue delivery of new affordable homes for social rent in South Lanarkshire with a total of 233 additional council homes during the year.
- The development of a short video to improve awareness of housing options and homelessness in secondary schools with active participation from homeless service users. This will be rolled out to education to incorporate into the school curriculum and shared with other services through 2023/24.
- A further 30 temporary homes converted to secure tenancies, best meeting the needs and choice of the household.
- Increase in social rented properties directed to homeless households, 58% of all vacant council homes and 38% of Registered Social Landlord lets in 2022/23.
- Continued progress raising awareness and testing approaches to homeless prevention via routine enquiry and collaborative response, informing priorities for coming year in relation to Homelessness Directions contained in the Strategic Commissioning Plan.
- Continued to support victims of domestic abuse through the implementation of specific housing pathway and housing representation at all Multi Agency Risk Assessment Conference (MARAC) meetings. Ensuring a multi-agency approach and resulting in successful work being carried out with 17 people through 2022/23.
- Evaluation of SHORE project reflected that the liberation process has enabled us to reduce the number of prisoners having to present as homeless and securing accommodation on their release. The dedicated SHORE worker engaged with 197 people, 70 cases were able to return to their previous residence and 9 with offers of accommodation.
- Continued growth of the Housing First approach with a further 3 households with multiple and complex needs supported during 2022/23, in addition to the cumulative 36 individuals supported through the programme. At year end 75% of Housing First cases have seen improvement in their overall outcomes.
- Increase in homelessness prevention through hardship sustainability funding and support services across all housing tenures.
- 81.8% improvement in distance travelled with internal housing support was recorded through the introduction of Wellbeing Web.
- High level of tenancy sustainment continues with 91% of homeless households sustaining their tenancy for over 12 months in 2022/23.

## 1. Background
### 1.1 National Context
While previous reviews have documented the dynamic context within which the RRTP is being implemented the fourth year of the plan, as noted above, has been progressed in the most challenging set of circumstances since the inception of the plan. A summary of key developments and challenges in the year is detailed below:

The links between homelessness and poverty are well documented, in 2022/23 there has been a continued economic downturn accompanied by the “cost of living crisis”. Global and national economies have been significantly affected by the impact of Covid 19 and the war in Ukraine which have directly impacted on the housing system. It is expected the challenges will continue to disproportionately impact on economically disadvantaged households who are at greatest risk of homelessness.

- ‘Preventing Homelessness in Scotland,’ a consultation published jointly by The Scottish Government and COSLA in December 2021, sought views on proposals to introduce statutory prevention duties across public bodies, re-emphasising the responsibility for preventing homelessness needs to be shared across community planning partners. The forthcoming Housing bill is expected to be published later in 2023 will clarify the legislative implications.
- Rapid Rehousing Transition Plans: Making the case for the next five years. The Chartered Institute of Housing Scotland (CIH) together with Fife Council published a report building on the work in July 2021 by CIH Scotland, highlighting the importance of Rapid Rehousing Transition Plans (RRTPs) as part of the Ending Homelessness Together commitment. Nevertheless, the Scottish Government has yet to confirm the requirements and expectations for RRTPs from 2024.
- A Temporary Accommodation Standards Framework was published by the Scottish Government in May 2023, intended to ensure all temporary accommodation throughout Scotland is of a consistently high quality. The framework covers the standards that should be achieved by all social landlords relating to physical, location, service, and management of temporary accommodation. The Scottish Government continue work to set out how standards will be monitored and enforced nationally.
### 1.2 South Lanarkshire Context
South Lanarkshire Council has a long-standing strong commitment to meeting the needs of homeless people. During 2022/23 the partnership focus on improving outcomes, both through prevention and response activity continued. This included the commitment set out in the Health and Social Care Partnership’s Strategic Commissioning Plan (2022-25).
The alignment of the RRTP with community planning was also further established during the year with the inclusion within the new “Community Plan 2022 to 2032” of the following high-level priority.
“We will work in partnership to prevent and significantly reduce homelessness and improve outcomes for those at risk of or who experience homelessness.”

### 1.3 Co-production and Oversight of the RRTP
The South Lanarkshire RRTP was co-produced through intensive engagement with key partners and this approach has been continued in the development, delivery, and review of the plan continuing to meet varying need, pressure on limited housing resources and the cost-of-living crisis.
The Homelessness Strategy Group who are responsible for monitoring and reporting in relation to the RRTP continued to meet throughout 2022/23.
A system of quarterly monitoring of the RRTP Measures and Actions was continued through 2022/23. This kept relevant stakeholders and senior management informed of progress throughout the year and provided the opportunity to raise awareness of Rapid Rehousing.
Senior managers from Housing and Technical Resources also attended regular meetings of the Housing Options West HUB meeting and represent the West HUB at the National Homeless Prevention RRTP subgroup, benefiting from shared learning across authorities and Scottish Government updates and discussions.
During 2022/23, further work continued to strengthen partnership links, ensuring homelessness and its wider impact is appropriately reflected in each strategy/plan. Key developments included: -
- The inclusion of the high-level priority relating to homelessness within the new “Community Plan 2022 to 2032”.
- the inclusion of homelessness prevention actions and monitoring within the Children’s Services (Corporate Parenting) Action Plan and Re-designing Children’s Services plan.
- the progression of two Homelessness Directions within the Health and Social Care Partnership’s Strategic Commissioning Plan (2022-25).
- the inclusion of action on homeless prevention within the Alcohol and Drug Partnership Strategy 2020-23 (Priority 4 A public Health Approach) and overall emphasis on early intervention and prevention.
- the inclusion of actions relating to homelessness within the Local Child Poverty Action Plan 2021/22.
- Continued focus on actions to support victims of domestic abuse from the Make a Stand pledge.

### 1.4 Funding
The Scottish Government awarded £453,000 to South Lanarkshire Council to fund RRTP	delivery during 2022/23. The total funding that was originally sought to support the RRTP	was £7.31million.
Since the first award of funding form the Scottish Government in 2019, and taking account of	the confirmed award for 2023/24 of £460,892 a total of £2,659,892 has been awarded to	support the development and implementation of RRTP, the breakdown is as follows:
RRTP funding received by year	Amount
2019	£105,000 (start-up funding)
2019/20	£461,000
2020/21	£453,000
2020/21	£282,000
2021/22	£445,000
2022/23	£453,000
2023/24	£460,892

It should be emphasised that partner contributions require to be considered broadly to include not only financial resources but other partner contributions such as realignment of staffing resources and service priorities to support delivery of the RRTP.
A summary of the key areas which have been progressed during the year using funding received from the Scottish Government’s Ending Homelessness Together Fund is detailed below: -
- Expansion of specialist support services to meet a range of complex need including repeat homelessness, multiple needs in particular addiction and mental health, further supported by Alcohol and Drug Partnership (ADP) funding.
- Scaling up of the Housing First approach to meet the needs of the most vulnerable offering greater choice and support to access and make a house a comfortable home.
- Continued focus on homeless prevention at points of transition in people’s lives, including the further development of the Sustainable Housing on Release for Everyone (SHORE)
- Continued delivery and further development of
  - approaches to Gender Based Violence and
  - housing pathway planning for young people moving on from care.
- The further development of services to prevent homelessness in the private sector through the Private Sector Access and Sustainment Service delivering advice along with practical and financial support to access and sustain private tenancies.
The original RRTP identified the need for £7.31million to resource the 5-year plan. To date £2,659,892 has been provided. The commitment for a further two years funding from the Scottish Government is welcomed. From the outset RRTP funding has been used to help establish or further develop key aspects of the RRTP. It should be emphasised that the overwhelming level of resources that partners have contributed to support delivery of the RRTP.
Experience across 2022/23 has shown that the high level of resources required to provide resilience is essential to maintain forward trajectory for homelessness when in context of the most challenging socio-economic circumstances.

### 1.5 Other funding sources
Throughout the period of the RRTP the partners within the Homelessness Strategy Group have worked together to actively consider alternative funding routes to take forward priority activities and identify opportunities to mainstream services and budgets to be revised or re-focused to help deliver RRTP priorities.
Progress was made in the year with:
- The Alcohol and Drug Partnership has also confirmed an allocation of £40,000 in year five of the plan to deliver services specifically designed to meet the needs of vulnerable women with addictions. ADP currently considering opportunities to further support prevention activity during 2023/34 including funding to increase SHORE, residential pathway plan and intensive support activities.
- South Lanarkshire Council contributed £10,000 towards delivering the SHORE project with a further £15,000 confirmed for 2023/24.
- Work across mental health and addiction services to remove barriers to access.
## 2 Homelessness Trends in the Year

During 2022/23, in line with national trends, homeless levels have spiked. The challenging economic climate, the “cost of living crisis” and changes in the private rented sector are thought to be driving the increased demand for homelessness services.
Over the last year South Lanarkshire has seen a 17% increase in homeless presentations and over 30% increase in the number of households assessed as homeless awaiting settled accommodation.

The Council is continuing to deliver quality homeless prevention and response services, striving to prevent homelessness where possible or effectively respond, with continued success across a range of measures for example reduction in repeat homelessness.

### 2.1 Humanitarian Assistance
This year has also witnessed a huge uplift in the level of support provided across the range of humanitarian programmes. This has included seeking to increase and support hosting arrangements and offering quality housing options advice.

The has required a significant increase in the involvement of local partners to support national refugee resettlement programmes, with the establishment of the “Homes for Ukraine Scheme” and the continued expansion of the “Afghan Resettlement Programme.” Additionally, in April 2022 the UK Government also announced its intention to implement a policy of “full dispersal” of asylum seekers with target levels of dispersal to each nation and region established during 2022/23. During 2022/23 the Council and other partners have actively engaged with COSLA and the Home Office to support implementation of the dispersal programme which it is anticipated will increase significantly in scale in 2023/24.

Given the on-going crisis in Ukraine and wider global uncertainty it can be anticipated that demand for housing and support services for refugees and people seeking asylum will significantly increase in the year/s ahead.

### 2.2 Homelessness demand
During 2022/23 South Lanarkshire played an active role in assisting Ukrainian households resettling in Scotland, over 600 people were accommodated in welcome hub hotel accommodation over the course of the year, 74 families were supported to settle in secure tenancies across our communities and the Refugee resettlement team also supported a further 188 individuals accommodated via host schemes.

Interim accommodation was developed at Barrack Street former student accommodation to provide accommodation and support services for 150 single Ukrainians. The service opened in January 2023, delivered in partnership with The Salvation Army offering an opportunity to move on from hotel provision, to find work and have time to make move on plans to other housing options e.g., private rented sector longer term.

South Lanarkshire’s focus on supporting households and delivering innovative solutions has helped prevent homelessness from humanitarian programmes within South Lanarkshire, also assisting nationally supporting the disembarkation of both the Glasgow and Edinburgh Ukrainian ships ensuring the smooth arrival of families into South Lanarkshire.

Alongside supporting Ukrainian nationals, the Refugee Resettlement service continued to support 53 refugee families (202 individuals) already settled in the local authority area and welcomed three new families who arrived as part of the Home Office UK Resettlement Scheme.

    1. Figure 1 below demonstrates the trend in the number of homelessness presentations received between 2002/03 and 2022/23, measured against the number of cases where the council had a duty to house the applicant and the number of cases that resulted in a Scottish Secure Tenancy being allocated upon case closure.
Figure 1 – Homelessness trends 2002-2023 Homeless Trends
- There has been a 17.2% increase in the number of homeless presentations, from 2134 in 2021/22 to 2502 in 2022/23. This is likely to be due to the external economic issues affecting the housing market including the reduction in turnover/availability, pressures in the private rented sector and the “cost of living crisis.”
- A rise of 9% in the proportion of households the council had a duty to house from 77% in 2021/22 to 86% in 2022/23.
- Continued high level of success in tenancy sustainment levels with 91% of homeless households sustaining their tenancy for over 12 months in 2022/23.
- Lets to homeless households both by the council and RSL partners have increased by 5% over the year (58% for council and 38% RSLs) despite a 14% fall in the total number of properties available to let.

### 2.3 Reasons for homelessness
Figure 2 below provides reasons for homelessness in South Lanarkshire in 2022/23.
Figure 2 – Reasons for homelessness
Reasons for Homelessness
There has been an overall increase in homeless demand locally and nationally. The success in reducing the backlog in the previous year has minimised the impact of this increase. The greatest increase has been seen in the areas below;
- Being asked to leave current accommodation continues to be the most common reason for homelessness in South Lanarkshire (28%) which is a slight increase on 2021/22 level of over 27%.
- Dispute with a violent partner account for 14.08% of all homeless presentations in South Lanarkshire, a slight increase of less than 1% on 2021/22 level.
- There is an increase in the levels of private rented across subcategories e.g., Landlord leaving the sector, a 150% increase over 3 years from 1 in 25 households to 1 in 10 since 2020/21.

2.3.1	By continuing to monitor RRTP data and its links to the Local Child Poverty Action Report, the partnership has continued to shape services to meet the needs of homeless households, to reduce the impact of poverty and homelessness, including likelihood of repeat cycles, aligning with Community Plan priorities.
2.3.2	Where homelessness cannot be prevented the partnership is keen to ensure needs and vulnerabilities are understood at the earliest opportunity to mitigate the impact of homelessness on health and well-being. In the last quarter 55 referrals were made to the Homelessness Nursing Service of NHS Lanarkshire, providing speeding access to the specialist nurse led team for assessment, direct support and referral onto specialist services as required.
### 2.4 Prevention of Homelessness
Figure 3 illustrates the number of cases managed by the council’s Housing Options service between 2018/19 and 2022/23 and details of the outcome of advice and assistance provided.

Figure 3 – Number of Housing Options cases and outcomes

Housing Options Cases and Outcomes

Positively, the increase in the number of housing option cases over the five years of the plan has also been accompanied by an increase in the proportion of cases where homelessness has been prevented to 65% in 2022/23. This underlines the positive difference the Housing Options approach continues to have preventing homelessness in South Lanarkshire.

There has been a significant focus on the development of prevention services over recent years, including during the period of the pandemic in preparation for an anticipated increased demand on this important first response to emerging housing need and risks.

### 2.5 Affordable Housing Supply (Social Rented)
2.5.1	Figure 4 below, provides details of the increase in social rented stock (owned by the council) across the four localities during 2022/23, RSL figures cannot be included until the Scottish Government Output report is published later.

Figure 4 – Total Social Rented Housing Supply by SLC (non-sheltered)

Description	Clydesdale	East Kilbride	Hamilton	Rutherglen/ Cambuslang	South Lanarkshire
RRTP Baseline (2018/19)	6,077	6,261	10,970	6,674	29,982
2022/23 SLC additions	7	92	79	55	233
Total	6,177	6,686	11,250	7,149	31,262

Throughout the fourth year of the RRTP and despite the challenges to the construction industry due to Covid-19, the council and its’ Registered Social Landlord partners have continued to increase the number of affordable homes for social rent across South Lanarkshire.

In the 2022/23, a total of 233 additional affordable homes were delivered by South Lanarkshire Council with 27% designed to meet the needs of those with particular needs, including wheelchair users.

### 2.6 Temporary Accommodation
Figure 5 below provides details of the supply of mainstream (self-contained furnished accommodation) by locality over the period since the RRTP was established.
   Figure 5 – Breakdown of mainstream temporary accommodation units by locality.

In addition to the council’s core temporary accommodation provision, self-contained furnished properties, ordinary homes across our communities, additional congregate living accommodation compliments the portfolio. This ensures immediate housing needs can be met, on a 24-hour 7 day per week basis. The council’s First Stop/Rapid Access Accommodation provides 61 units of safe, welcoming accommodation with staff providing appropriate assistance and support. There are also 49 units of specialist supported accommodation and 26 units of refuge accommodation through Women’s Aid.

The greatest increase in temporary accommodation placements has occurred in relation to B&B usage which has increased by 89.8% since the same period last year, albeit starting from a very low level of only 30 placements during the course of 2022/23. This is as a result of increased demand for temporary accommodation and the impact of severe weather over winter months which required significant use of properties to decant tenants and less lets available overall despite % lets to unintentionally homeless households increasing and the unusually high lets in in 2021/22 due to the 657 new build properties in the year.
2.6.1	Following a review of Temporary Accommodation undertaken during 2021/22 a Temporary Accommodation Strategic Plan was developed in 2022/23. This strategy and associated planning tool have aided:
- modelling supply to meet varying need and unprecedented increase in demand
- consideration on the Councils approach, resulting in the decision to close Lindsay House and re-locate to separate sites East Kilbride First Stop provision and the required level of specialist supported accommodation, to modern appropriate accommodation
- A more robust process for continual monitoring and review of temporary accommodation requirements
2.6.2	The process of “flipping” temporary units to Scottish Secure Tenancies has continued, with 105 units having been converted to a permanent home for homeless households since the implementation of the RRTP in 2019 with a focus on planning for longer term cases.
Case Study: Flipped Tenancy / A service user who had mobility issues and suffered from poor mental health had settled and was doing very well in their temporary furnished flat. Their occupational therapist had assessed that the property was medically suitable and the following discussions the property was converted to a permanent settled home. This alleviated the stress of another move and the challenge of identifying a permanent tenancy that would meet the applicants’ medical needs.

Quote from Service User: Flipped Tenancy / “…thrilled to keep the temporary accommodation and happy in the tenancy.”

2.6.3	Figure 6 provides a comparison of the average number of days spent in temporary furnished accommodation (excluding First Stop, Supported) between 2019 (RRTP baseline position) and 2022/23
South Lanarkshire Council’s temporary accommodation planning, and monitoring processes have ensured consistent provision of suitable temporary accommodation with any use of unsuitable options such as bed and breakfast being minimal and very short term, there has therefore been no breaches of the Unsuitable Accommodation Order to report. Although this has been increasingly challenging over the last year with the increase in demand for temporary accommodation requiring significant increase in use of bed and breakfast accommodation, conservation of the optimal use mainstream temporary accommodation is a foremost consideration of the council.

Figure 6 – Average number of days spent in temporary furnished accommodation by Locality.

- The South Lanarkshire average number of days spent in self-contained temporary furnished accommodation decreased by 20% from 226 in 2020/21 to 181 days in 2021/22 and is now decreased a further 4% in 2022/23 to 174 days at the lowest point since the RRTP was approved.
- The average time spent in temporary furnished accommodation varies significantly by area, from 108 days in Clydesdale to 232 days in East Kilbride. The South Lanarkshire average being 174 days. This is due to higher demand and greater pressure on accommodation in more urban localities. Across all temporary accommodation types the average length of stay was 95.7 days.
2.6.4	At the end of 2022/23 a 65% reduction in homeless households living in temporary accommodation for more than 12 months has been secured since the beginning of the RRTP. This underlines the positive impact which the partnership is having and allows a positive projection to achieving an end to long-term homelessness in South Lanarkshire within the five-year timescale of the RRTP. Reducing long term homelessness numbers is a key area of focus for partners despite the challenging context and progress in relation to this.

### 2.7 Repeat Homelessness
2.7.1	During 2022/23, there has been a decrease in the proportion of repeat homelessness cases compared with the previous year from 5.6% in 2021/22 to 3.6% in 2022/23. There continues to be an increased focus on support, particularly for those with complex needs, which contributes to improvements in tenancy sustainment and prevention of repeat homelessness. Analysis of repeat homelessness is continuous informing future service development.
Relatively low levels of rough sleeping continue to be reported across South Lanarkshire, from 69 reported instances during 2021/22 to 25 instances reported during 2022/23 a 64% decrease. All actions developed in the Rough Sleeping Action Plan in 2021/22 are now complete, this included introducing online reporting, promotion of 24-hour service availability in response to urgent homelessness contributing to successful reduction in instances of rough sleeping. However, this remains an area of focus into 2023/24.
## 3. Year Four progress
### 3.1 Tackling homelessness
Tackling homelessness requires a shared commitment from a range of agencies and	partners in the public, private and third sectors. As such the RRTP was co-produced and	annually reviewed with partners and stakeholders involved in the decision-making process	for agreeing ongoing priority actions contained within the plan.
### 3.2 Reviewing the plan
The Homelessness Strategy Group has responsibility for monitoring progress in relation to the RRTP and overseeing the annual review, including the evaluation of progress against actions and measures set out within the action plan and consideration of the appropriateness of the actions identified.
During the process of reviewing the fourth year of the RRTP, it has been recognised that progress has built upon the existing foundations of strong partnerships, and this will ensure the continuation and further development of key areas of work, particularly in light of the continually challenging environment. The group note good progress has been made over the last four years meeting key objectives whilst adapting to the impact of the public health emergency, and a solid structure is in place enabling the achievement of positive outcomes.
### 3.3 Review Scorecard
To monitor progress against each of the five priority objectives in the RRTP, a traffic light scoring system is used. Attached to the priorities are 53 indicators comprising of 33 actions and 20 measures. A further category of blue was an addition to the second annual review and highlights actions which have been completed. Figure 7 below provides a summary of the position in relation to the progress made towards the achievement of the five priority objectives of the RRTP during 2022/23. Over 92% of indicators were either achieved or were close to target.

Figure 7: Scorecard
RRTP Scorecard 2022/23	Blue	Green	Amber	Red	Grey	Total
Prevent homelessness occurring and significantly reduce homelessness	1	10	1	2	0	14
Significantly reduce time spent by households in temporary accommodation and minimise moves before moving to settled homes	0	11	1	0	0	12
Improve and increase the provision of housing support for households to live independently within communities	1	9	1	0	1	12
Expand the scope and capacity of our Housing First approach to be the first response for households with multiple complex needs	0	9	0	0	1	10
Enhance integration and partnership working to embed RRTP through a whole systems approach	1	4	0	0	0	5
All	3	43	3	2	2	53

Colour	Progress
Blue	Complete
Green	Achieved/on target
Amber	Minor slippage
Red	Significantly off target
Grey	Report Later/Contextual

### 3.4 Key Highlights of Progress Made in Year 4
Detailed below are key highlights of the progress that has been made towards delivering the actions and measures outlined for Year four for each of the five RRTP priority objectives. Some examples of service user feedback and case studies have also been provided to demonstrate the positive outcomes achieved.
A summary of progress made in Year four, in relation to all actions and measures detailed in the RRTP Action Plan is also attached as Appendix 1.
Priority Objective 1: Prevent homelessness occurring and significantly reduce homelessness
Although early intervention and integrated housing options has continued in line with national trends there has been an increase in the levels of homelessness. Success in reducing the backlog over the previous year can however be considered to have limited the impact of this increase. / A further improvement of availability in affordable housing has been seen in 2022/23 with a total of 233 delivered (this included 57 purchased through the Council’s Open Market Purchase Scheme). / There has been a continued partnership approach with Right There to support access and sustainability of tenancies in the Private Rented Sector with the continuation of the Innovation Fund. In 2022/23 there were 24 people helped through the scheme. / In 2022/23 there was a continued focus on early detection of housing risk factors and interventions to prevent homelessness where possible through the Integrated Housing Options model. Despite an increase in the demand for the service 65% of advice cases were closed with support being provided preventing homelessness from occurring. / Improved service pathways developed between the Integrated Housing Options Team and Adult Employability Services supporting adults at risk of homelessness to access education, training, or employment. / Ongoing pathway approach to support those affected by domestic abuse with a view to preventing homelessness wherever possible. With 17 people supported through the year by a part time post the aim is to expand this service through 2023/24 with additional funding from the Alcohol and Drug Partnership. / Ongoing joint approach to supporting young people moving on from a care setting through pathway plan process and additional support available via Social Work’s Throughcare and Aftercare team in close partnership with Housing Services. / A homelessness awareness video co-produced with service users details journeys through homelessness was shared with partners including a service user group. The feedback from all service users who viewed the video was very positive noting this was an informative resource relating to homelessness prevention and homelessness services. The video is now being shared in Education, wider Council Departments, Women’s Aid and Commissioned Services to share with those at risk of or actually homeless across the partnership.

Case Study: Innovation Fund / We received a call from Lanark housing service looking for some advice regarding a male single parent that had contacted housing after the sudden death of his wife. / He was living in a private rented property with his 12-year-old son, and both were finding it difficult living there due to his wife passing away in the property. This was very traumatic for them and was affecting their mental health. The father made reference to preferring to be homeless than continuing to reside at the property due to the trauma he and his son had faced. / The client had identified an alternative property through his current private sector landlord but didn’t have the finances to pay the deposit required to secure the property. / Unfortunately, the landlord would not accept the standard guarantee bond for the deposit, however we were able to support through the Innovation Fund and arranged for a cash payment to be paid directly into the landlord's account facilitating a move within 2 weeks. We were also able to help with decoration cost for the son’s bedroom to support him to settle well in his new tenancy by accessing a starter pack fund. / The client expressed his gratitude to the service and explained that without the help of Right There , there would have been no way he would have been able to afford the deposit required to move and that they have both settled in well to their new home which has had a significant impact on the child’s welfare, education and both father and son’s general wellbeing.

Case Study: Domestic Abuse Housing Pathway / AM was first presented at MARAC in September 2020 with her partner. They had two homeless applications prior to this date for fleeing the threat of external violence. Anti-social behaviour complaints from their tenancy stated the perpetrator was regularly arguing or violent towards neighbours and the victim. Since 2019 there were more than five complaints concerned for the welfare of the victim. / The perpetrator was imprisoned May 2021 for domestic abuse offences. AM made it clear to Housing Officer that once perpetrator was released from prison, she did not wish to continue the relationship. AM indicated that she wished to remain in the tenancy, so the Housing Officer tried various routes to seek his removal from the joint tenancy. This was not successful. The perpetrator refused to sign over the tenancy even with the offer of alternative accommodation on his release. Legal services were unable to assist as he had joint rights to the tenancy. / The perpetrator was released from prison May 2022 and headed straight for their tenancy where it was suspected the domestic abuse, including financially abuse, restarted. / The following week the victim attended an appointment in a council office and the perpetrator found her there and assaulted her. He was arrested and released with bail conditions. AM presented to the out of hours service that evening with Police, she was very subdued and did not speak to staff. Later the following day she was found to be in possession of an unknown substance and was asked to leave and alternative accommodated had to be sourced. / AM began to engage with Social Work, community addictions team, Women’s Aid and ASSIST. She was also diagnosed as schizophrenic. / The Housing Officer completed a domestic abuse Housing Pathway with AM. She has since been rehoused in another locality, a safe distance away from her previous joint tenancy where he continues to reside. This took 239 days from the date she applied as homeless to the date her new tenancy started. Outreach housing support service has been put in place and she engages well with this and the other agencies.

Priority Objective 2: Significantly reduce time spent by households in temporary accommodation and minimise moves before moving to a settled home
A further 4% reduction in the number of households who have spent more than 12 months in temporary accommodation. / A 65% reduction in long term homelessness from 120 in 2019/20, 56 in 2020/21, 42 in 2021/22 and 40 in 2022/23. / A 4% reduction in time spent in temporary accommodation from an average of 181 days in 2021/22 to an average of 174 days in 2022/23. This not only reflects improvements on a very challenging year but sees a 7% reduction compared against pre-pandemic levels. / An increase in the number of temporary tenancies which were ‘flipped’ to a Scottish Secure Tenancy, providing the homeless household with a permanent home, and avoiding the need for the disruption of further moves. A total of 105 tenancies have been flipped since 2019/20 / The Council and its HomeFinder Registered Social Landlord (RSL) partners continue to maximise the percentage of lets to be directed to those on the Homeless List. In 2022/23, 58% of council properties were let to homeless applicants. HomeFinder RSLs collectively let 38% of vacant properties to homeless households. / There continues to be a low incidence of rough sleeping in South Lanarkshire with a 60% reduction in those who advised they had slept rough the night before presenting as homeless over the lifetime of the plan.

Priority Objective 3: Improve and increase the provision of housing support for households to live independently within communities
Tenancy sustainment levels remain high at 92% for overall tenancies and 91% for previously homeless households. The HomeStart service contributes to this positive position with continued focus on assisting new council tenants, (in particular those at most risk of or who have experienced homelessness), to sustain their tenancy. In the last year, the HomeStart service provided both practical assistance and advice to 1235 new tenants helping set up a comfortable home. / Improved integration of housing support services - Partnership work with Salvation Army, Turning Point, Blue Triangle Housing Association and Right There has supported the continued development of the pathway planning approach which ensures the provision of innovative housing support projects across South Lanarkshire. All congregate living temporary accommodation projects offer quality, person centred support in a “psychologically informed environment.” Support is designed to build personal resilience, strengthen social networks, and empower, including increasing life skills to support tenancy sustainment. An Intensive Floating Support service is also provided to households with multiple and complex needs. / A dedicated focus, with specialist posts, deliver a positive Personal Housing Planning approach for vulnerable groups including women experiencing domestic abuse, care leavers, and the continued implementation of SHORE standards for the prevention of homelessness on release from prison remains. / Ongoing partnership approach to meeting the needs of women at risk of homelessness due to gender based violence. Housing represented on Co-corporate GBV partnership group in addition to Housing subgroup with purpose of raising awareness of issue, supporting learning and development across workforce, and delivering person centred pathway plans to explore all housing options and secure suitable sustainable housing outcomes. / The complex need case discussion panel has continued through 2022/23 with a planned calendar of meetings and flexibility for emergency panels as required. The focus has been on encouraging the sharing of knowledge, skills, and insight from partners in Health and Social Work with the panel to target interventions and improve the quality of life for clients and reduce further homelessness and the impact of homelessness as far as possible. / Service users were offered the opportunity to attend Harm Reduction training through the Service User Engagement programme resulting in positive feedback enabling those who attending to use their skills to assist their peers. / The Wellbeing Web was introduced in 2022/23 to enable better understanding and monitoring of housing support need and outcomes achieved. The service supported 485 clients over the course of the year achieving 81.8% improvement against assessed support needs, this includes managing a home, addiction, mental health, and community connections.

Case Study: Complex Case Panel / Service user presented as homeless due to being asked to leave by his Mum. He had a diagnosis of ADHD and his behaviours in the family home were causing distress to his two younger sisters. His Mum felt she could no longer cope with him in the house but still wanted to provide a level of support. / Housing Support Officer assessment lead onto referral for discussion at the complex need case panel. Abusive behaviour was a key concern. / A meeting was arranged and the Housing Support Officer, Homeless Team Leader, Social Worker, representation from Blue Triangle Intensive Floating Support, Health & Homeless and Right There discussed an approach to meeting accommodation and support needs. / It was considered abusive behaviours seemed linked to the ask to move on from the family home, a feeling of isolation and placement out with the area he had grown up in. / The panel agreed the following actions: - / Identify a temporary furnished flat in close proximity to his family. / Referral onto outreach support service and Social Work to look at providing and funding appropriate service for additional support needs. / Housing Support Officer to work with client to complete detailed housing plan so we could establish the best areas to be rehoused permanently. / Following the agreed plan of action, a Temporary Furnished Flat was identified 0.3 miles from Mum’s house. Joint discussion and support in place lead to agreement on temporary return to the family home until this property was available to move into solving immediate accommodation concerns. A referral was made to Right There and a male support worker picked up the case. Social Work continued to work with the family in considering the most appropriate supports. / After moving into the Temporary Furnished Flat he settled quickly. The family relationships improved greatly as he had his own space but Mum close by for support. Across the partnership support was delivered and well received on a voluntary basis. After five months of a settled position, it was agreed to ‘flip’ the tenancy to a Scottish secure tenancy. / The positive outcomes for this case: - / Multi agency approach met support needs. / Person centred housing plan identified most appropriate accommodation option. / Appropriate offer of housing through flipping tenancy preventing further disruption. / Positive relationships established should there be any future need for advice or support.

Priority Objective 4: Expand the scope and capacity of our Housing First approach to be the first response for households with multiple complex needs
South Lanarkshire Council in partnership with The Salvation Army continue to work to deliver Housing First support to individuals with multiple complex needs. / In 2022/23 a further 3 individuals were supported through Housing First totalling 36 supported since the service began. Improvement in outcomes for individuals supported by Housing First has been recorded in areas such as a 22% increase in engagement around drug & alcohol use, in turn a 5% decrease in offending behaviour, 12% increase in motivation & taking responsibility, 3% increase in management of tenancies and 3% increase in self-care. / As the individual learns they gradually become more self-reliant; this is maximised by the number of hours staff were available to support service users by arranging for staggered starts, shift working, and/or encouraging staff to work flexible hours. / Continued growth of the partnership Community Harm Reduction Hub enabling those supported by the Housing First service to access group work, harm reduction intervention, psychosocial implementation and build on life skills. / Further support through Health and Wellbeing began in 2022/23 with the implementation of a walking group for Housing First service users. / Progress made over last year with prioritising access to general medical and universal health screening services for homeless people particularly positive partnership with community links health team. During 2023/24 work will continue to explore opportunities to expand and evidence prevention activity through priority access.

Service User Feedback/Comments: Housing First Service / “Thanks to everyone at Housing 1st for their help and support over the last few years. I’d have been lost without all of you, they are all diamonds yourself included so thank you, you all do an amazing job”. / “Thanks very much for everything that you’ve done for me, guiding me. If it wasn’t for you, I wouldn’t have come this far”. / “This Service has saved me, like mentally and physically. There is nothing that staff wouldn’t do to support me and are always there to make sure I am ok. My treatment can take it out of me sometimes but just knowing that someone cares make it all worthwhile. I feel stable in my home and feel as though this is my time.” / “The staff helped me with cooking.” / “I hide away, and my worker always makes sure that I get the things I need. I struggle but always tried to act as though I was managing. It’s good to have people know me”. / “If it wasn’t for staff and this Service I would probably be in and out of hostels and prison. This is the longest that I have not spent time in prison. My house looks amazing.” / “I have been going to the groups at the HUB, never usually go anywhere as I struggle with people. It is really fun and even get to meet new people”. / “Yesterday, I bought my own furniture. Some I have to do things too, but it is mine and felt really good”.

Priority Objective 5: Enhance integration and partnership working to embed RRTP through a whole systems approach
Regular update on partner services is provided to the Homelessness Strategy Group which improves knowledge and understanding of the role of each partner and promotes best practice and consistency for governance of the plan. / The Homelessness Strategy played an active role in shaping the homelessness content of the new Local Housing Strategy (LHS) 2022 to 2077 which was approved in November 2022. / Close partnership working continues to develop and progress specific ‘Directions’ within the Strategic Commissioning Plan 2022-25. Progress made over last year includes positive partnership with community links health team. During 2023/24 work will continue to explore opportunities to expand and evidence prevention activity through priority access. Evaluation will be undertaken by end of 2023 which will allow sufficient time to take account of the of legislation and statutory guidance on new prevention of homelessness duties for public bodies in the forthcoming Housing Bill. / The council has also successfully agreed an information sharing arrangement with the National Health Service enabling data trend analysis to understand links between health and homelessness data with a view to aiding preventative activity. / Data sharing on an individual basis in relation to household with children has been re-established to ensure the impact of homelessness is minimised

### 3.5 Key Areas for Improvement
3.5.1	Progress is being made with 92% of indicators on the RRTP Action Plan being complete, on target or close to target, however there are three indicators across the five priority objectives that have been allocated an amber status and two which are now red and these will continue to be areas of focus and improvement during 2023/24.
3.5.2	Table A below provides the context as to why they continue to be monitored.
Table A – Red and Amber Measures
Reference	Measure	Comment
M1.1	The number of homeless Presentations	This action, in line with national trends, the demand for homelessness services increased significantly in the year, a 17% increase. This trend is likely to continue in light of external factors including socio-economic circumstances. It is therefore considered necessary to increase RRTP measure from a target to reduce homelessness by 10%-20% and replaced (see 4.3 Table B – Proposed Amendments below)
M1.2	Level of Homeless Households (homelessness caseload at year end)	As above the spike in demand for homeless services has resulted in the measure now being red and the likelihood of meeting the target unlikely. Nationally homeless applications are at the highest since collections began in 2002, with an increase of 29% compared to 2019 reported by the Scottish Government in January 2023. It is therefore proposed that this measure will be removed from the RRTP and replaced (see 4.3 Table B – Proposed Amendments below)
M1.5	Increase the number of landlord accredited properties	Through the Private Landlord Forum, private landlords are encouraged to take up training offered by Landlord Accreditation Scotland. This measure will continue to be progressed during 2023/24.
M2.3	Percentage of homeless households provided with a Scottish Secure Tenancy	While performance reduced during the year in the face of a number of external challenges there has been a 4% improvement when considered over the last 2 years. There is confidence that over the next year the performance will improve further.
M3.1	Number of people accessing Housing Options (prevention) services	Slightly under target for 2022/23 however a positively the proportion of cases where homelessness has been prevented was 65%. This underlines the positive difference the Housing Options approach continues to have on preventing homelessness in South Lanarkshire.

## 4. Proposed Changes to Rapid Rehousing Transition Plan (RRTP)
The annual review provides the opportunity to assess and report on the progress made against each of the actions and measures contained within the plan. It also allows for a general re-examination of the RRTP, to ensure that the objectives, actions, and measures identified, remain appropriate, relevant, and measurable.
During the annual review one proposed revised action has been identified. Details of the proposed change are detailed in Table B below. Following approval, the revision will be incorporated into the RRTP action plan for 2023/24.

In addition, several minor amendments have been made throughout the action plan to measures and actions to reflect changes in processes or updated terminology. These do not impact on the outcomes reported; however, help ensure the RRTP remains up to date and clear in how it will deliver the intended outcomes.
Table B – Proposed Amendments
Ref.	Current action/measure	Status	Ref.	Proposed replacement action/measure (where appropriate)
M1.1A	The number of homeless Presentations	Red	M1.1	It is looking increasingly unlikely that the target to reduce by 10%-20% will be met due to the increasing pressures from external factors out with the control of the authority. Although the focus on prevention work will continue. / It is proposed therefore that the target for this measure be amended to “maintain or reduce the level of homeless presentations in the year.”
M1.2A	Level of Homeless Households (homelessness caseload at year end)	Red	M1.2	It is looking increasingly unlikely that the target to reduce by 10%-20% will be met due to the increasing pressures from external factors out with the control of the authority. / Although the focus on prevention work will continue, it is proposed that the target for this measure be amended to “maintain or reduce level of homelessness.”

## 5. Priorities for 2023/24
The review also provides an opportunity to set out the key priorities to be progressed over the next year of the plan.
A summary of these to be progressed during 2023/24 are detailed below: -
- Continue to deliver affordable homes for social rent.
- Ongoing focus on prevention of homelessness, particularly in relation to households with children through continuing to maximise social lets to homeless households and continued support to access and sustain in relation to the private sector.
- Continue to reduce long-term homelessness.
- Further progress the homelessness directions contained within the Strategic Commissioning Plan.
- Continue to maintain and develop links to the Local Child Poverty Action Plan.
- Monitor implementation of specific pathways for victims of domestic abuse, with additional of ADP funded specialist support.
- Continue to work with Social Work Resource to develop housing options for young care leavers, including supported accommodation model.
- Further develop the approach for individuals released from prison by expanding the service by linking in with female prisons.
- Continue to focus on pathways and a Housing Options approach for young people.
- Continue to develop, promote, and monitor the Private Sector Access and Sustainment Service.
- Review the councils Homestart service for new tenants for decision on future and to capture learning to inform future service development.
- Continue to expand councils Housing First approach.
- Continue to convert temporary units to permanent accommodation.
- Complete review of support service provision and identify proposals for implementation of revised approach to commission and delivery of trauma informed support services.
- Continue the focus on joined up approaches and avoid long-term duplication of services. especially with health and social care partnerships and community justice.
- Review of Commissioned Services exploring opportunities of partnership working for efficiencies and to lever in funding that will add value to existing homelessness services.
- Further progress ongoing work with RSL partners to expand Homefinder Common Housing Register.
### 5.1 Funding the RRTP during 2023/24

Scottish Government Funding
During 2022/23, the Scottish Government’s Ending Homelessness Together Fund confirmed a funding allocation of £460,892 for year five for South Lanarkshire. Partners agreed that this would be used to further embed and progress the following RRTP actions: -
- The expansion of specialist support services currently provided by Blue Triangle Housing Association for intensive floating support services to individuals with complex needs.
- Continuation of funding dedicated officer posts to support victims of domestic abuse.
- Continued support of the Private Sector Access and Sustainment Service and expansion of the Innovation Fund administered by Right There.
- Continuation of funding dedicated officer posts to support young care leavers.
- Continuation of funding dedicated officer to support SHORE standards for individuals entering and leaving prison.
- The continuation of the Housing First programme.

Other Funding Sources
The Homelessness Strategy Group actively consider other potential funding routes to meet future resourcing requirements of the RRTP. Partners have committed to work collaboratively to identify funding opportunities in 2023/24.
ADP have provided £40k to support delivery of SLC’s RRTP in relation to funding two part-time posts within Blue Triangle Housing Association (BTHA) to support vulnerable women with addictions.
The posts have been advertised and recruitment is now complete for one and underway for the second. It is anticipated that the posts will provide valuable support to vulnerable women with addictions to enable them to engage with services and to develop the necessary knowledge and skills to successfully manage their home and sustain settled housing.
There is a bid being submitted jointly with BTHA to Young Scot. If successful, this bid would fund a post to support young people in South Lanarkshire. It is hoped the funding could also give the opportunity to work with New College Lanarkshire to develop an accredited course to provide young people with basic life skills that are essential in setting up a home including cooking and budgeting.
Another potential funding source is also being pursued jointly with BTHA in a bid to Tesco fur a small sum to fund an infographic and short video to assist in setting up a home. This will be aimed again at young people however could be utilised for all new tenants.
## Appendix 1: RRTP Action Plan

Priority Objective 1: Prevent homelessness occurring and significantly reduce homelessness
RRTP Measures		Target	RRTP Baseline	Progress 2022/23	Lead
M1.1	Number of homeless presentations	Maintain or reduce	1,928	2502	HTR
M1.2	Level of Homeless Households (homelessness caseload at year end)	Maintain or reduce	892	1331	HTR
M1.3	Number of affordable homes added to the housing supply (new and OMP)	Annual target will be set and detailed in the Strategic Local Programme Agreement, developed between SLC and the Scottish Government	RSL 283	To be reported later	HTR / RSL
			SLC 193	233
M1.4	New supply affordable housing suitable to meet particular needs	Annual target will be set and detailed in the Strategic Local Programme Agreement, developed between SLC and the Scottish Government	170	63	HTR / RSL
M1.5	Increase the number of accredited landlord properties	+9% from LHS baseline	1,068	942	HTR
M1.6	Number of homeless households whose housing needs are met in the private rented sector	Increase 2020/21	50	39	HTR

Priority Objective 1: Prevent homelessness occurring and significantly reduce homelessness
Actions		Target/Milestone	Progress in 2022/23	Lead
A1.1	Set housing supply targets for new build properties and ensure contribution to meeting homelessness needs are considered in the planning process	Aligned with Strategic Housing Investment Plan and the Local Housing Strategy. Annual target will be set and detailed in the Strategic Local Programme Agreement, developed between SLC and the Scottish Government.	New build programme progressing in accordance with South Lanarkshire Strategic Housing Investment Plan 2022-27 approved by Housing and Technical Resources Committee in November 2021.	HTR/RSL
A1.2	Increase number of properties acquired through Open Market Purchase (OMP Scheme) to support conversion of temporary accommodation to secure tenancies and rehousing in pressure areas	Annual target to be agreed in Strategic Housing Investment Plan.	57(53 - 21/22) additional council homes were purchased through the council’s framework for Open Market Purchase Scheme. The scope of the was extended follow approval at HTR committee on 14/12/2022 to allow for properties that have been empty for a period of more than 12 months to be considered for purchase without being actively marketed for sale. / The changes also allow owners of former council properties to contact the council and for direct discussion to take place with the owner themselves and the council to engage with private landlords who are already leasing their property to the council on the potential purchase of this.	HTR
Priority Objective 1: Prevent homelessness occurring and significantly reduce homelessness
Actions		Target/Milestone	Progress in 2022/23	Lead
A1.3	Continue to develop and promote the landlord accreditation scheme	Deliver two private landlord forums per annum in partnership with the Landlord Accreditation Scotland	South Lanarkshire Council has continued to promote the accreditation scheme at forum meetings and the Council’s websites. There are 942 registered landlords in South Lanarkshire.	HTR
A1.4	Provide funding to incentivise landlords to access accreditation and training from Landlord Accreditation Scotland	Annual fees provided and accreditation monitored	The council continues to fund and work in partnership with Landlord Accreditation Scotland who provide training to private landlords. The accreditation scheme is free to join and once accredited, landlords are required to attend one training session per year.	HTR
A1.5A	Expand the Private Sector Access and Sustainment Service administered by Right There	Service Expanded – by DATE / Monitor effectiveness of increased capacity and widening scope of service delivery	Right There (formally Ypeople) provide expert advice and assistance, assessing housing needs, risk to sustainment in particular financial risk and assist households access and sustain private sector accommodation. / In 2022/23 £3,500 of financial assistance was provided through Guarantee Bonds in place of a cash deposit	HTR /Right There
A1.6A	Deliver and continue to develop Private Sector Innovation Fund administered by Right There - providing financial support to private rented tenants to prevent homelessness.	Service continues to be delivered in accordance with – commissioning contract.	The Innovation Fund administered by Right There's Private Sector Access and Sustainment Fund (PSASS), has seen increased demand. A total of £15705.50 has been administered in financial assistance.	HTR/ Right There
Priority Objective 1: Prevent homelessness occurring and significantly reduce homelessness
Actions		Target/Milestone	Progress in 2022/23	Lead
A1.7A	Continue to develop and implement approaches to prevent youth homelessness, with a particular focus on pathway approach to meeting the needs of care experienced young people.	Continue to deliver personalised and planned approach to provision of housing for young people leaving care. / New Pathway Approach implemented by March 2023	This year we continued our Housing Pathways approach for all care experienced young people within the Throughcare system. Partners set a target in the year for 95% of applicants in the throughcare route to have a person-centred housing pathway agreement in place.	HTR
A1.8	Continue to develop and implement approaches to support victims of domestic abuse and prevent homelessness.	Enhance the development of the housing pathway for victims of domestic abuse and considering legislative changes and good practice	During 2022/23 we have continued to provide housing representation at every MARAC, sharing relevant information on victims and perpetrators and taking away appropriate actions agreed at each meeting with the goal of maximising safety planning to safeguard victims.

Priority Objective 2: Significantly reduce time spent by households in temporary accommodation and minimise moves before moving to settled homes
RRTP Measures		Target	RRTP Baseline	Progress 2022/23	Lead
M2.1	Temporary Accommodation Supply	Complete review of options for the provision of temporary accommodation in 2022/23 in conjunction with implementation of the Temporary Accommodation Strategic Plan to maintain optimum supply.	Units 530	Units 609	HTR
M2.2	Percentage of social housing allocated to homeless households by all social housing providers in South Lanarkshire	50-60% / Set target subject to annual review	49.2% SLC / 29.4% RSL	58.14% / 37.90%	HTR/RSL
M2.3	Percentage of homeless households provided with a Scottish Secure Tenancy (SST)	Maintain/improve on LHS baseline of 61.2%	61.2%	57.77%	HTR
M2.4	Percentage of former homeless households provided with an SST that maintain their home for more than 12 months	Maintain/improve on LHS baseline of 88%	88%	91%	HTR
M2.5	Average time spent in temporary accommodation	Reduce from 192 days	192 days	173.72	HTR
M2.6	Number of temporary accommodation units converted to SST	Up to 100 units converted over 5-year period		30 units / (105 in total)	HTR
M2.7	Percentage of all homeless presentations which are repeated (within 12 months)	Reduce to less than 3%	4.5%	3.6%	HTR
M2.8	Number of homeless households who spend more than 12 months in temporary accommodation	Reduce by 50% on baseline	120	40	HTR

Priority Objective 2: Significantly reduce time spent by households in temporary accommodation and minimise moves before moving to settled homes
Actions		Target/Milestone	Progress in 2022/23	Lead
A2.1A	Maximise the potential for converting temporary accommodation to a Scottish Secure Tenancy where the property meets the needs of the household	Review best practice and identify suitable households and units	30 units have been flipped during 2022/23. This continues to be an area of strategic focus and Area Teams continue to achieve a balance between flipping and keeping quality temporary accommodation in the right places.	HTR
A2.2	Increase percentage of allocations to homeless households	SLC aligned with Local Letting Plans. / RSL partners as per agreed targets	The council continues to allocate between 50% and 60% of lets to homeless households. Some RSL HomeFinder partners were below their individual target. Cumulatively RSL HomeFinder partners allocated 38% of vacant properties to homeless households in 2022/23. To support delivery of the RRTP, the council continues to work with RSLs to secure the necessary proportion of their vacant properties are directed towards meeting the needs of homeless households during the year.	HTR
Priority Objective 2: Significantly reduce time spent by households in temporary accommodation and minimise moves before moving to settled homes
Actions		Target/Milestone	Progress in 2022/23	Lead
A2.3	Review number of properties currently used as temporary accommodation in line with demand	Reconfigure targets for temporary accommodation provision in 2022/23 subject to analysis confirmed in Temporary Accommodation Strategic Plan	The development of a Temporary Accommodation Strategic Plan completed which included development of a modelling tool for forecasting targets for temporary accommodation beyond 2024. See section 2.4 for details. / Annualised target for number of properties used as temporary accommodation to be set based upon plan from 2023/24	HTR
A2.4	Regularly review rent charges for temporary accommodation to ensure it remains a financially viable option for all homeless households.	Aligned with Homelessness Business Plan	Further work to ensure rent affordability opportunity being progressed as part of the implementation Temporary Accommodation Strategic Plan.	HTR

Priority Objective 3: Improve and increase provision of housing support for households to live independently within communities
RRTP Measures		Target	RRTP Baseline	Progress 2022/23	Lead
M3.1	Number of people accessing Housing Options (prevention) services	1,000	964	972	HTR
M3.2A	Percentage of homeless households who require support, provided with Housing Support Officer assistance	Maintain at 100%	100%	100%	HTR
M3.3	Percentage of looked after young people accessing and sustaining accommodation that meets their needs	Determine baseline / Increase annually	95%	93%	HTR

Priority Objective 3: Improve and increase provision of housing support for households to live independently within communities
Actions		Target/Milestone	Progress in 2022/23	Lead
A3.1	Increase housing support service provision to improve homelessness prevention and support tenancy sustainment across all tenures.	Review current service provision	Range of internal and 3rd sector partners continue to deliver housing support services, both in prevention activity and response to homelessness minimising its impact. / Monitoring of housing support outcomes reflects positive outcomes, reduced need across all wellbeing/support need indicators and increasing tenancy sustainment. / The Wellbeing Web was introduced 2022/23 to enable SLC to monitor and track progress of households engaged with Housing Support Workers. / The impact of the Wellbeing Web recording, monitoring, and reporting demonstrates the level of housing support needs across SLC, particularly in relation to provision of supports in relation to managing the home, finances, mental and physical health and employment and education. / The introduction of the Wellbeing Web has provided an opportunity to understand our service users needs across localities and the distance they have travelled to achieve desired outcomes that will help them sustain a settled tenancy.	HTR
Priority Objective 3: Improve and increase provision of housing support for households to live independently within communities
Actions		Target/Milestone	Progress in 2022/23	Lead
A3.2	Increase provision of support from all services to support new tenancies, including improvements to housing starter/furnishing packs and incentives to encourage uptake of offers.	Review and develop / Implement and monitor effectiveness	The HomeStart service was established permanently during 2021/22. During the year, the service has continued to assist 1235 new tenants settle into and sustain their new tenancy through assessing risk factors such as previous eviction or homelessness and financial risk, offering information and advice from benefit entitlement, employment, and training opportunities to practical support for example around budgeting, reducing debts and making community connections. The service includes provision of starter pack furniture as required.	HTR
A3.3	Monitor current Housing Options approach, and ensure adequate resourcing to meet any future increase in demand	Annually monitor resourcing requirements and report through annual review	While performance is marginally below the prevention target the focus on person-centred approach continues to support positive outcomes.	HTR
A3.4	Deliver Housing Options and homelessness awareness training to young people, targeting high schools in areas identified with high homelessness rates amongst young people	Monitor and report	Improved awareness of housing options and homelessness by secondary school pupils due to the development of a film that incorporated into the school curriculum with active participation from homeless service users. Service users enjoyed this experience and considered it valuable to provide an overview of the impact of homelessness.	HTR

Priority Objective 3: Improve and increase provision of housing support for households to live independently within communities
Actions			Target/Milestone		Progress in 2022/23			Lead
A3.5	Review access to Scottish Welfare Fund with a view to ensuring effective and appropriate access for homeless households.		Complete Review / Implement any actions from review		Good partnership working across services with regular liaison meetings, good communication and awareness of urgency for homeless households. SWF team utilised additional funding to increase support to homeless household aiding sustainment over the last year.			HTR
A3.6	Review current provision and need for outreach housing support and agree future service arrangements		Complete Review. Current services/contracts due to end and implement revised arrangements as result of review		To be reported later			HTR
A3.7	Ensure ‘care experience’ is identified as a support need for any young people presenting as homeless and directed towards appropriate case managed pathway.		Monitor and report		There have been positive outcomes and improvements to processes due to effective joint working between Housing and Social Work. The joint protocol will continue to be monitored and reported to senior management annually. / Use of pathway plan, which compliments with wider Children’s plan enables comprehensive person-centred housing and support planning and delivery.			HTR
Priority Objective 3: Improve and increase provision of housing support for households to live independently within communities
Actions			Target/Milestone		Progress in 2022/23			Lead
A3.8	Complete a Wellbeing Assessment for all children and young people who are homeless		Monitor and report (annually)		A process for a “request for assistance” is now in place to highlight affected children both to health visitors and school nurses. Housing and NHS Lanarkshire Health Improvement team working towards development of a process for wellbeing assessments for children affected by homelessness through the school nurse service.			HTR
A3.9	Promote digital inclusion for households who are homeless		Maximise funding for the provision of digital equipment and two year’s unlimited internet access for homeless households		Since 2019 108 homeless households and vulnerable young adults have benefited from the continued efforts to challenge digital exclusion through the Bringing IT Home project. Each household has received a piece of digital equipment and two years of unlimited internet access.			HTR
Priority Objective 4: Expand the scope and capacity of our Housing First approach to be the first response for households with multiple complex needs
RRTP Measures				Target		RRTP Baseline	Progress 2022/23		Lead
M4.1		Number of current households receiving Housing First Support		Phased increase to 40		3	36		HTR
M4.2A		Number of Housing First planning cases handled by health professional led multi-agency care management approach.		Baseline to be established		-	See Action A4.8		HTR/HSCP

Priority Objective 4: Expand the scope and capacity of our Housing First approach to be the first response for households with multiple complex needs
Actions		Target/Milestone	Progress in 2022/23	Lead
A4.1	Expand Housing First across South Lanarkshire	40 cases to be progressed on period of RRTP - 2019-24	During 2022/23, an additional 3 cases were included in the programme bringing the total households who have been supported to 36.	HTR
A4.2	Evaluate Housing First pathfinders and increase scale/scope of approach aligned to case conference criteria and pathways approach	Evaluation Report to be completed	To be reported later	HTR
A4.3A	Complete development of the Temporary Accommodation Strategic Plan and progress implementation	Implementation of Temporary Accommodation Strategic Plan and reconfiguration of temporary accommodation model.	The Temporary Accommodation Strategic Plan has been developed and annual reviews are underway to enable a complete understanding of how temporary accommodation is used and how it can be best developed to meet demand over the medium and longer term. It has been agreed that due to the increase in demand on the homeless service the modelling tool which was developed in support of the plan in 2021/22 will be redone to inform the future provision of temporary accommodation.
A4.4	Work with Scottish Prison Service and Addiewell prison to implement SHORE standards for people entering and exiting prison, including a priority focus for short-sentence prisoners on remand. Explore additional options for dedicated staff resources	Implementation plan agreed for implementation from 2020/21	The liberation process has enabled us to reduce the number of prisoners having to present as homeless and securing accommodation on their release. There have been 5 service users that have received housing at release. Quarter 4 seen 3 further offers from the Other Category list. Ongoing we are continuing to track cases, ensuring tenancies are sustained and working in partnership with Justice Throughcare Services to support and prevent re-offending where possible.	HTR
A4.5	Increase awareness and increase training offered to front line services to support people impacted by Adverse Childhood Experiences (ACEs) from being homeless	Evaluate requirement to raise awareness of partners in relation to ACEs.	Service Development Sessions continue to be delivered to Housing Officers and Housing Support Officers across locality operational teams to raise awareness of trauma and providing a psychologically informed environment.	HTR
A4.6	Identify requirements for intensive trauma informed and PIE residential supported accommodation to meet the needs of extremely vulnerable groups	Complete scoping report	Relevant Housing/Support Officers included in ACE's and PIE training delivered on partnership approach across Housing, Health and Social Care delivered by Right There. Managers participated in Trauma Informed Practice awareness. This will continue to be an on-going focus for partners.	HTR
A4.7	Promote ‘routine enquiry’ across all health and care services, including visiting outreach, to identify housing provision and financial security	Monitor and report via Health and Homelessness Steering Group	Continued commitment to improving homelessness prevention has been achieved through the publication of the Strategic Commissioning Plan (2022-25) will provide opportunities to improve early intervention where recognised triggers of homelessness are identified. Arrangements are in place between housing and the Health and Social Care Partnership to progress this direction in 2023/24.	HTR/HSCP
A4.8	Prioritise access to general medical and universal health screening services for homeless people, including primary care (GP), prescribing, dentists, etc	Monitor and report via Health and Homelessness Steering Group	Progress made over last year particularly positive partnership with community links health team. During 2023/24 work will continue to explore opportunities to expand and evidence prevention activity through priority access. / Evaluation will be undertaken with a formal report to the IJB by end of 2023. / This will allow sufficient time to take account of the of legislation and statutory guidance on new prevention of homelessness duties for public. / bodies in the forthcoming Housing Bill.	HTR/HSCP

Priority Objective 5: Enhance integration and partnership working to embed RRTP through a whole systems approach
RRTP Measures		Target	RRTP Baseline	Progress 2022/23	Lead
M5.1	Number of training and employment pathways for homeless households	To be agreed	To be agreed	4	FCR

Priority Objective 5: Enhance integration and partnership working to embed RRTP through a whole systems approach
Actions		Target/Milestone	Progress in 2022/23	Lead
A5.1	Work with DWP to further develop use of discretionary support funding for homeless households to undertake appropriate training to develop skills and resilience to improve access to employment	Agree pathways for accessing discretionary support with DWP	DWP continue to work with the council and a range of third sector organisations to ensure claimants who are homeless/at risk of homelessness are offered relevant and timely support.	HTR/DWP
A5.2	Explore options for improving digital connectivity for all homeless households, increasing engagement with services, and enabling improved tenancy management	Explore options for expansion of project	Utilising RRTP funding, the Bringing IT Home project was expanded. Since 2019 108 homeless and vulnerable households have been provided with digital devices and unlimited internet access for 2 years.	HTR
A5.3	Ensure effective training for staff is in place on awareness of the third sector support available to people at risk of homelessness in each locality	Implement improvements as required	VASLAN continue to be represented within the RRTP partnership for raising awareness of third sector support within South Lanarkshire.	TS
A5.4	Contribute to ongoing development and review of homelessness business plan to ensure sufficient resources available to continue to provide high quality services to homeless households	Implemented recommendations as required	Progress against Homelessness Business Plan is monitored on an ongoing basis throughout the year, through monthly performance report and at mid-year and year-end review.	HTR

If you need this information in another language or format, please contact us to discuss how we can best meet your needs. Phone 0303 123 1015 or email equalities@southlanarkshire.gov.uk